## MyVest (hidden)
Release | Feature | Rel | xFR | Delivery Status | PGM | Prod MGR | PRD Target | PRD Actual | Dev Target | Dev Actual | Feature Sign-off | PME | IEE | Curr | Var | % Var
xx
| Release Owner | ?? |  |  |  | Release Status
| Target Release Date | TBD |  |  |  | PRD Complete Milestone:
| Actual Release Date |  |  |  |  | Feature Sign Off Milestone:
[12 empty] | #REF! | #REF! | #REF! | #REF!
| Unquirk | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Code coverage improvements | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| TD Ameritrade | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Schwab | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Fidelity | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Continuous integration testing for web services | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Trade Netting Block Level | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Pricing Hierarchy | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Spring Upgrade 4.3.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!

## AM (hidden)
Release | Feature | Rel | xFR | Delivery Status | PGM | Prod MGR | PRD Target | PRD Cust Sign-off Actual | Dev Target | Dev Actual | Feature Sign-off | PME | IEE | Curr | Var | % Var
AM-2016-10
| Release Owner | David |  |  |  | Release Status | Delivered | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2016-10-26 | g |  |  | PRD Complete Milestone: | N/A | g |  |  | MV Testing Complete Target | 2016-10-25 | g
| Actual Release Date | 2016-10-26 | G |  |  | Feature Sign Off Milestone: | N/A | g |  |  | Cust Testing Complete Target | 2016-10-25 | g |  |  |  | % over PME | % over IEE
[12 empty] | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| Trade Bulk Cancel Phase 2 - Trade Recon | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Custodial Endpoints - Open Lots | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Bulk Rebalancer Phase 2 - remaining scope | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Trade Bulk Cancel Phase 1 - Trade Recon | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| SMI Model Change Impact Web Service | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| SMI Model Change Impact Web Service-MV Scope | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
AM-2016-11
| Release Owner | David |  |  |  | Release Status | Delivered | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2016-11-23 | g |  |  | PRD Complete Milestone: | N/A | g |  |  | MV Testing Complete Target | 2016-11-22 | g
| Actual Release Date | 2016-11-23 | G |  |  | Feature Sign Off Milestone: | N/A | g |  |  | Cust Testing Complete Target | 2016-11-22 | g |  |  |  | % over PME | % over IEE
[12 empty] | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| Resolve STAR issue around coupons | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fractional shares in STAR | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
AM-2016-12
| Release Owner | David |  |  |  | Release Status | Cancelled | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2016-12-22 | g |  |  | PRD Complete Milestone: | N/A | g |  |  | MV Testing Complete Target | 2016-12-21 | g
| Actual Release Date | N/A | G |  |  | Feature Sign Off Milestone: | N/A | g |  |  | Cust Testing Complete Target | 2016-12-21 | g |  |  |  | % over PME | % over IEE
[12 empty] | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| Account Recon Improvements | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| CRM Team Creation Web Service | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Updates were only deployed to UAT
AM-2017-01
| Release Owner | David |  |  |  | Release Status | Delivered | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-01-25 | g |  |  | PRD Complete Milestone: | N/A | g |  |  | MV Testing Complete Target |  | g
| Actual Release Date | 2017-01-27 | G |  |  | Feature Sign Off Milestone: | N/A | g |  |  | Cust Testing Complete Target |  | g |  |  |  | % over PME | % over IEE
[12 empty] | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| Custodial Endpoints - Closed Lots | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | N/A | #REF!
| Portfolio Management Program Enhancements-IM | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0%
| Portfolio Management Program Enhancements-ADV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Open Order Deletion - page - Ops console | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Targeted Rebalance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
AM-2017-02
| Release Owner | David |  |  |  | Release Status | Cancelled | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-03-01 | g |  |  | PRD Complete Milestone: | N/A | g |  |  | MV Testing Complete Target |  | g
| Actual Release Date | N/A | G |  |  | Feature Sign Off Milestone: | 2017-02-22 | g |  |  | Cust Testing Complete Target |  | g |  |  |  | % over PME | % over IEE
[12 empty] | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| Advisor-managed Preferences (QPR) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Dividend accrual treatment - performance calc | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4/4 - release to be reconciled
AM-2017-04
| Release Owner | David |  |  |  | Release Status | Not Started | r |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-04-26 | r |  |  | PRD Complete Milestone: | TBD |  |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | r |  |  | Feature Sign Off Milestone: | TBD |  |  |  | Cust Testing Complete Target |  | g
[12 empty] | #REF! | #REF! | #REF! | #REF!
| ADVUI - Household Overview Page | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
4/19 - team leads notified to add Household Overview Page to change log to move to July release. As a result, there will be no deliverables for April. Once the release is updated, the RAG status will be lowered.
AM-2017-05
| Release Owner | David |  |  |  | Release Status | In Dev | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-05-31 | g |  |  | PRD Complete Milestone: | N/A | g |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: | 2017-05-23 | g |  |  | Cust Testing Complete Target |  | g
[12 empty] | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| ADVUI - MyBook Page | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| ADVUI - Transactions | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| ADVUI - Performance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| ADVUI - Realized Gain/Loss | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| ADVUI - Tax Shield | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| ADVUI - Export Daily Returns from On-Demand Reporting | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
4/19 - Release date corrected for the last day of the month. Team leads notified to update change log for "Export Daily Returns" to align with the release.
AM-2017-06
| Release Owner | David |  |  |  | Release Status | Not Started | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-06-28 | g |  |  | PRD Complete Milestone: | TBD |  |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: | TBD |  |  |  | Cust Testing Complete Target |  | g
[12 empty] | #REF! | #REF! | #REF! | #REF!
| ADVUI - Holdings | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| ADVUI - File Cabinet | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
4/19 - Release date corrected
AM-2017-07
| Release Owner | David |  |  |  | Release Status | Not Started | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-07-26 | y |  |  | PRD Complete Milestone: | TBD |  |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: | TBD |  |  |  | Cust Testing Complete Target |  | g
[12 empty] | #REF! | #REF! | #REF! | #REF!
| ADVUI - Iframing and Sponsor Specific Changes for AssetMark | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| ADVUI - Advisor Managed Preferences - UI Work | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
4/19 - release date corrected. Team leads notified to add the Iframeing and Sponsor specific changes to the August release.
AM-2017-08
| Release Owner | David |  |  |  | Release Status | Not Started | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-08-30 | y |  |  | PRD Complete Milestone: | TBD |  |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: | TBD |  |  |  | Cust Testing Complete Target |  | g
[12 empty] | #REF! | #REF! | #REF! | #REF!
| Document Delivery | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Ability for Investor to Edit Fields | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Risk Informed Performance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Advisor Uploaded Logo | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Advisor View | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| IP Sleeve Performance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Market Value vs Net Investment Over Time Graph | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
4/19 - release date corrected for the last Wednesday. Team leads notified to add Market Value vs. Net Investment to change control to move this to the September release.
AM-2017-09
| Release Owner | David |  |  |  | Release Status | Not Started | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-09-27 | g |  |  | PRD Complete Milestone: |  |  |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: |  |  |  |  | Cust Testing Complete Target |  | g
[12 empty] | 0 | 0 | 0 | 0
4/19 - release date corrected.
UI ADV OnB
| Release Owner | David |  |  |  | Release Status | Not Started | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-09-30 | g |  |  | PRD Complete Milestone: |  |  |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: |  |  |  |  | Cust Testing Complete Target |  | g
[12 empty] | #REF! | #REF! | #REF! | #REF!
| Portfolio Attributes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Profile | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| UI Start | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Select Strategy | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Questionnaire | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Infrastructure | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Fees | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Accounts | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Accounts2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Portfolio Goals | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Cash Instructions | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Prospect List | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Proposal Document | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Manual Assets | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Customize Strategy | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
- Comment 1 - Comment 2
UI EZ Button
| Release Owner | David |  |  |  | Release Status | Not Started | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-09-30 |  |  |  | PRD Complete Milestone: |  |  |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: |  |  |  |  | Cust Testing Complete Target |  | g
[12 empty] | #REF! | #REF! | #REF! | #REF!
| Allow advisor to select from two proposal types | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Create Goal | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Display suggested strategies | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
4/19 - confirmed with Product Mgmt that UI EZ Button is phase 2 and provided that this will be approved. Change Control request to be entered to cancel these items.
AM-2017-10
| Release Owner | David |  |  |  | Release Status | Not Started | g |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2017-10-25 |  |  |  | PRD Complete Milestone: |  |  |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: |  |  |  |  | Cust Testing Complete Target |  | g
[12 empty] | #REF! | #REF! | #REF! | #REF!
| SPS Investor Portal | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
4/19 - email to team leads to confirm that a change control entry should be put in to move this to a November release.
Patches
|  | Release Date | JIRA Link | Purpose | RO Signoff | RM Signoff
Non-release Activities |  | MV Owner | Status | Target Comp Date | Comments

## BBVA (hidden)
Release | Feature | Rel | xFR | Delivery Status | PGM | Prod MGR | PRD Target | PRD Actual | Dev Target | Dev Actual | Feature Sign-off | PME | IEE | Curr | Var | % Var
BBVA Release 1
| Release Owner | Rob |  |  |  | Release Status | On Hold | y |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2018-09-07 | g |  |  | PRD Complete Milestone: |  | g |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: |  | g |  |  | Cust Testing Complete Target |  | g
[12 empty] | 0 | 0 | 0 | 0
Prepopulate forms for Pershing and FIS
Docu-Sign Integration
Salesforce Integration
MoneyGuide Pro Integration
SPS Client Play Back
Data Aggregation
Tax Budget Integration with Optimizer
Before and after analysis
Unknown
Fixed income detail page in QPR
Spanish reporting (Investor portal, proposal, QPR)
Fact sheet upload on per proposal basis
Integrate to display additional data in proposal
Generate and display additional data in proposal
Alternative landing pages in Investor Portal based on client type.
Automatically pull in Morningstar Direct Reports into Proposal Document
Drift Triggered Rebalance
Update / Test Alerts for Share based models
Create request for though Investor Portal
Integration with sharepoint
Statements in Spanish
Sector Substition
Auto sent blocks under 5k shares
Bins for fixed income types
Performance Attribution
Export to First Rate
Fee schedule by AssetClass
Digital Collaboration Tools
BBVA data aggregation
Performance Dispersion
Investor Portal
Investor Portal II
Customized Proposal
Customized QPR
T+1 settings for Mutual Funds
Coupon Payments
New Read Web Services
Trade Trigger column to be added to MPM table
Investment Change History Page
Trades posting to Eagle/STAR with wrong NetAmount
Recon Reorgs
Comment:
Dependencies for BBVA Go-Live
| Release Owner | Rob |  |  |  | Release Status | On Hold | y |  |  | MV Dev Complete Target |  | g
| Target Release Date | 2018-09-07 | g |  |  | PRD Complete Milestone: |  | g |  |  | MV Testing Complete Target |  | g
| Actual Release Date |  | G |  |  | Feature Sign Off Milestone: |  | g |  |  | Cust Testing Complete Target |  | g
[12 empty] | #REF! | #REF! | #REF! | #REF!
Dependencies for BBVA Go Live:
| Trading partner connectivity | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Trading partner connectivity - MV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| 401K /403B account types don't match XSD picklist | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Trade Auto-Posting :Trade Matching for Trade/Non-Trade Reversals | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Link SMAs to Models | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Sleeve Performance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Calculate / match realized gain/loss per transaction | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| TD Ameritrade | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Bank Holiday Support (multiple calendars)-IM | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Income SWP Reserve | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Composite Reporting | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Schwab | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| FIdelity | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| MF MV - Sungard connectivity | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Conversion Tool - Load and Store Historical MVs and Performance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| MV - SGN Allocation connectivity | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Convert and store historical transactions | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| ADVUI - Transactions | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Bank Holiday Support (multiple calendars)-OPS Data | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Bank Holiday Support (multiple calendars)-OPS APP | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Enhanced Data Validation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| IP Sleeve Performance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Account Aggregation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Pricing Hierarchy | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Data Mart Creation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Bulk Rebalancer | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| OPM Dashboard Enhancements | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Pershing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Account Hold Management - from Ops Console | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Model Change Alert and Workflow | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Trade Bulk Cancel Phase 1 - Trade Recon | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Trade Bulk Cancel Phase 2 - Trade Recon | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Fractional Shares in Star | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Resolve STAR Issue Around Coupons | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Account Recon Improvements | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Open Order Deletion - page - Ops Console | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Portfolio Management Program Enhancements-IM | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Targeted Rebalance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
| Dividend accrual treatment - performance calc | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | g | #REF! | #REF! | #REF! | #REF! | #REF!
- Above list describes all known and potential requirements based on current discovery. Discovery is incomplete so this list may change. - "E-AM Cancelled" and #N/A Items (requirement-confirmed) have been listed on the Change Control tab so that these are re-incorporated in capacility and SDLC plan. - #N/A items (not yet requirement confirmed) will not be requested as additions to the SDLC until we ratify the project scope and confirm initial scoping estimates.
Patches
|  | Release Date | JIRA Link | Purpose | PM Signoff | QA Signoff | SME Signoff | RO Signoff
Non-release Activities |  | MV Owner | Status | Target Comp Date | Comments

## 2017Cap (hidden)
#REF!

## Master
[13 empty] | 2019-01-15 | 2019-01-29 | 2019-02-12 | 2019-02-26 | 2019-03-12 | 2019-03-26 | 2019-04-09 | 2019-04-23 | 2019-05-07 | 2019-05-21 | 2019-06-04 | 2019-06-18 | 2019-07-02 | 2019-07-16 | 2019-07-30 | 2019-08-13 | 2019-08-27 | 2019-09-10 | 2019-09-24 | 2019-10-08 | 2019-10-22 | 2019-11-05 | 2019-11-19 | 2019-12-03 | 2019-12-17 | 2019-12-31
Project | 2021 Plan Days | Work Stream | Start Date | End Date | Project Schedule Delivery Expectations | Release Date | Person Days | # Team Mem | Total Days | Architecture Discussion Status | Project Status | Notes
Web Application for Car Review | 354 | New Development | 2021-01-02 | 2021-11-30 | 2021-12-15 | 2021-12-22 | 66.4 | 5 | 332 | In Progress | In Progress | Divided project activities based on 2 weeks sprints | bar: 2019-01-15 to 2019-11-19
Appendix
Requirement Analysis
Model & Design
Requirement & Model Sign Off
Product Development
QA & Deploy

## TTRAN WS to Rel Matrix (hidden)
Workstream | Go/No Go Participant | GP Dependency | 3rd Party Dependency | MV Release? | TIAA Release? | Release | Decommission req'ed? | Biz Process Change?
Custodial Integration | MV, TIAA | Yes | SEI | Yes | No?
Trading | MV, TIAA, FIS, PERF | Yes | FIS, PERF | Yes | No | FIS must be released/turned on.
Web Services | MV, TIAA | No | - | Yes | Yes | Together
Environment Split from Openwealth | MV, TIAA | Yes | GP | Yes | No
Data Mart | MV, TIAA | No | - | Yes | ?
Operational Reporting/ Data Extracts | MV, TIAA | No | - | Yes? | ?
QPR/Proposal Printing | MV, TIAA | No | Harte Hanks | No | No
Operations | MV | ? | - | Yes | No
Product Management | - |  | - | - | -
QA/UAT Testing | - | No | - | - | -
Audit/Regulatory | - | ? | - | - | -
Tech Ops / Production Support | ? | No | - | No | No
Contractual Evaluation | - |  | - | - | -
Project Management | - |  | - | - | -
Operations Utilities | MV | Yes | - | Yes | No
JIRA Integration | ? |  | - | JIRA | ?

## (Pre-AM Cleanup Backup) Change (hidden)
Date Opened | ID | JIRA Key | Issue | Prty | Cust | Added By | Current Action Owner | Pgm Team | Status | Scope Impact | Impacted Release | Change Type | Notes | X-Ref
2016-05-01 | 1 |  | GICS 3.0 - SunGard - Re-certification of TWAP/VWAP (Convergex) - SunGard and Pershing connectivity | B | GP |  | Heather | IM | Closed | 5 |  |  | 8/11 - Heather to get PME / IEE and assess timing for when this is necessary 8/18 - Estimated and added to the Capacity Plan 10/12 - hm: Planning to test week of 10/25.
2016-05-06 | 2 |  | Additional CP Items #2 - OFR added 5/16 | 15 | GP |  | Heather |  | Closed |  |  |  | 8/11 - Heather to determine when this may be delivered given 16.1 / CP schedule change 8/11 - Sajid verified this item is complete in 16.1 and will update the AMMO for the SDLC line item. 10/12 - hm: Closing as this was delivered.
2016-06-01 | 3 | N/A | GP Integration Environment Data Scrubbing - As part of the AWS Envir agreement MV comitted to deliver "data scrubbing" to remove PII as part of a data clone from Prod | B | GP | Chris | Chris | N/A | On Hold |  |  |  | 1/26/17- current status: Joe has finished all scripts needed. Next steps: 1) Chris to line up the staging environment for testing Joe's script. Won't have an update until at least week of 1/30/2017. 2) Go-live: detailed steps here: https://docs.google.com/spreadsheets/d/1m2pRwuwZYGjPAqF0ySex2xVSAuazqV3Obct_LonQR0o/edit?ts=588a42c2#gid=814972615
2016-07-05 | 4 |  | GICS 3.0 - Morning Star Morningstar GICS Data Feed Schema Change - Mandated on Aug 31 | A | GP |  | Heather | ON | Closed | 8 | None |  | 7/25 - Joanne assessing effort and creating AMMO. Need to add this to SDLC Tracker. 8/11 - Underway for Aug 31 10/10 - Made part of the 16.1 release. Closing
2016-07-05 | 5 |  | Morningstar Rating for Funds Change - Oct. 31, 2016, Morningstar will enhance the calculation for the Morningstar Rating™ for Funds | B | GP |  | Josh |  | Closed |  |  |  | 7/5 - Josh to assess the impact of this chance and if any development effort is necessary. 8/24 - To go out in 16.1 release, as requested by client 10/12 - hm: Closing as this was delivered with 16.1
2016-07-10 | 6 |  | BBVA - This is a new customer potential - not previously accounted for in the plan. | B | BBVA |  | Mike |  | Closed | 1200 |  |  | 7/21 - Current proposed target is EO-Q3 2017 - assuming under contract by 9/1/16. 9/8 - Assume under contract by November 1
2016-07-10 | 7 |  | PCAP 16.1 Release Scope definition for the Personal Capital release - Need to conduct a review of the proposed items once the reaminder of H2 is recast due to scope issues. - Renaming release to 16.3 to avoid confusion. | A | PC |  | Rasaan ./ Heather |  | Closed | 70 | PCAP 16.1 |  | 8/11 - Finalize available capacity & which PCAP items fit by 8/16 (Heather). 8/11 - Requires all open 16.1 / 16.2 / AM4 / AM5 / AM6 scope assessed as a prerequisite. 8/18 - Rasaan to lay out options for how to use the allcoated 145 days for PC in 2016 8/25- options sent. Mark/Rasaan to discuss in the week of 8/29. 8/29 - Agreed to move AM6 multiple trade order blotter to AM 7 to create IM capacity for PCAP in 2016. Change capacity plan. 8/31 - Also want to look at possible other delivery alternatives to achieve the budgeted DR in 2016 9/8 - Rasaan to finalize final revenue items & review with Mark 9/15 - Added to SDLC and Capacity Plan 10/10 - Final review with Chery and Rasaan needed. 11/7 - MW: Changing reference name for this release to 16.3 for clarity (incorporates 16.1 as baseline)
2016-07-20 | 8 |  | Fall Line Securities - This is a new customer via Genpact | B | FL |  | Chris |  | Closed | 148 |  |  | 8/1 - Need proposal / estimates for delivery. GP anticipating January 2017 launch?? 8/25 - Chris/Josh/Brian to review GP's feedback. 9/1 - Chris to schedule a status review / kickoff.
2016-07-20 | 9 |  | DMA - PME versus FEE | B | GP |  | Brian |  | Closed | 65 | 16.1 |  | 8/8 - PMEs came in at 273 D, IEE came in at 338 D. We should understand why to improve estimates going forward 8/11 - Brian to call retrospective to sumarize where estimate changes occured 9/1 - Closed 10/12 - hm: Closing as this was delivered.
2016-07-28 | 10 |  | Custodial End Points - RMD estimates to be complete by 8/5 | A | AM |  | Joel |  | Closed |  | AM 4 |  | 8/8 Custodial EPs Pricing (PRD, RMD complete), Positions (PRD, RMD complete, Transactions (PRD complete, RMD signoff this week), Lots (PRD in progress, RMD, to start) 8/4- discussion still opens among joel, kevin, frederic, arlene and natalia as to whether this is one or multiple endpoints. 8/11- Scheduled to review Custodial Endpoint reconciliation on Friday 8/12 (Heather). 8/11 - The reacrhitecture for account recon has been built in to the pricing for Custodial EP for Pricing. 8/25- RMD completed. Added to capacity plan. 10/12 - Closed Lots RMD and IEE required to finish this. 10/24 - hm: Closing as Lots is a line item above
2016-07-28 | 11 |  | 16.1.1 16.1.2 16.2.1 DMA Follow-up Releases have "new functionality" but were not recorded on the SDLC Tracker. - They need to be added and the capacity impact needs to be assessed. | A | GP |  | Brian |  | Closed | 96 | 16.1.1 16.1.2 16.2.1 |  | 7/29 - Chris to coordinate with Brian - add rows for the missing scope items. 8/1 - Items added under "DMA P1, 2, 3" Release identifiers. Lines 159 -165. Need estimates for all 8/11 - Need PME for Edit Fee Schedul Webservice - Patch 1 items 8/12 DMA P1 and P2 added to Capacity Plan 08/08 Control. Still need to add P3 to 2017 10/13 - hm - Close out
2016-07-29 | 12 |  | Model creation / change web service integration between SMI and SPS - (AFR-18) - Scope increased to add 2 additional web services | B | AM |  | Heather |  | Closed | 12 |  |  | 8/1 - Target to have PRD / RMD updates by 8/5 8/11 - PRD/RMD updated - underway for AM4 10/12 - hm: Closing as this has been delivered.
2016-07-29 | 13 |  | PA Cost Base Changes (tax lots from Pershing) - Can be removed from 16.1 release per Brian | B | GP |  | Joanne |  | Closed | -101 |  |  | 8/1 - Updated on SDLC to remove it from 16.1. 8/1 - Brian / Chris to confirm Descoped = no longer necessary 8/11 - Check with Ops Data RE redundant with AM Interface?? (Joanne) 8/26 - capacity plan updated and closed.
2016-08-01 | 14 |  | AssetMark4 Proposed replan - Change scope to have 3 Custodial EP (Pricing, Positions, Transactions), Model Change Alert, Webservices for SMI model /strategy, CRM integration web services - Assess impact to AM5 | A | AM |  | Heather / Rasaan |  | Closed |  | AM 4 |  | 8/8 - Model Change Alert (scope), Custodial Endpoint (effort estimate) 8/12 Estimates and projects added to Capacity Plan 08/08 Control 10/12 - AM releases are now monthly. This line item is addressed by mutliple other line items in the control log.
2016-08-01 | 15 |  | (Not in Master) Fidelity moving from Pull to Push - Mandated change in delivery method to take effect on ?? | B | AM |  | Josh |  | Closed |  |  |  | 8/11 - Not a Program Team impact - work to be executed in new setup for Fidelity by Client Deliery 10/25 - hm: Josh, Client delivery need to rearchitect. Put on AM issues list?
2016-08-01 | 16 |  | Advanced Search - Need to assess when we can get in. 16.2? | C | GP |  | Heather | ADV | Closed | 45 | Consider |  | 8/11 - Determine if fits in capacity plan (Heather) 8/11 - Agreed to put on hold until re-escalated by GP 10/10 - Closing as GP has not made this a priority and PM would like to make changes we feel best product solution. No changes were made to Master or Capacity plan.
2016-08-08 | 17 |  | Custodial Endpoint Postion - Account Recon being re-architected in this scope? | A | AM |  | Chris |  | Duplicate |  |  |  | 8/11 - Review outstanding RECON items from GP & verify they are reflected. Also review with team UI items specifically. (Chris) 10/12 - Closing , duplicate of Account recon rewrite
2016-08-08 | 18 |  | Pricing Hierachy - Unclear when this came into SDLC / why? | A | AM | Heather | AnnP | Ops Data | Closed | 54 | Consider |  | 8/8 - Proposed for AM5 - Need PME / EO for Capacity ASAP 8/11 - Verify base level hirachy support & review Bloomberg & IDC conversion to accomodate (Heather) 8/11 - Object Model changes and support for Bloomberg and IDC are part of the Custodial EP Pricing RMD. Bloomberg is being implemented as part of the Pricing EP. IDC will be implemented later. Small increment to IDC implementation to test for pricing hierarchy. 8/16 - Mike brought up a great point that we need to be careful with distribution of custodian pricing information. For example, we may not have permission to publish pricing from Fidelity in a QPR. Need to investigate (Mark?) 8/18 - The estimate in an email from Josh had a total estimate of 54 days, 12 of which was the back end data so I pulled that piece out since it should be captured in the custodian end point work. 8/24 - Capacity plan updated with 42 days for Ops Data 10/25 - hm: Was this done as part of CE pricing loading? If so was all the work complete by this work ? If no then what is left to be done. Spoke with AnnP, she is putting together the EO. The assumption above that the BE work was covered by CE Pricing was incorrect. 11/29 - hm: Brian do we really need this?
2016-08-08 | 19 |  | Conversion - web services to add fields required Conversion - modify web services to add fields required by AM - Unclear when this came in / how critical | A | AM |  | Brian |  | Closed |  | AM 6 |  | 8/8 - Proposed for AM 6 8/11 - Need target dates for (PME / PRD / RMD) ASAP 8/16 - Began PRD for household, portfolio, account web services; will work with Advisor program to get estimate. 9/22 - Shenba finishing up PRD and Brian to get EO in SDLC. 10/6 - Shenba needs to give an update an EO. 10/13 - hm: EO and Actuals now entered, eo-60d, actual 61d. Shenba was this completed? 10/20 - bkm: This is in Master, suggest we close 10/20 - hm: Add RMD, dev complete target, slot for a monthly release in 2017. Need during the Mock time. 10/24 - hm: This has an actual. Brian and Shenba is this complete. 10/27 - bkm: yes, PRD is done. 11/2 - hm: 68 D in Harvest towards this project. Chris will audit.
2016-08-08 | 20 |  | Need to review CDA (AM) with Justin / Brian - Requirements from customer are unclear and likely to have material increase in scope / estimate | A | AM |  | Brian |  | Closed |  |  |  | 8/8 - Goal is to validate CDA estimates and breakdown into smaller tasks 8/16 - Phase 1 - CDAs for standing instructions (withdrawals) have been defined. Working on next set of CDAs with AM. This will need to be broken up into phases. 8/25 - PMs to start writing PRD's for Phase II. 8/31 Arlene and Dan reviewed requirements, this is mostly IM work and as a result will affect IM capacity. Waiting for RMD details. 9/22 Expecting additional info from customer 10/7 10/20 bkm: Suggest we close this until we get a requirement from customer and then we can add a new line item along with estimate. 10/20 - hm: closing till we get new CDA workflows
2016-08-08 | 21 |  | Future Dated Trade for CRT - Came in between 7/15 - 8/8 - Is scope essential - when really needed | A | AM |  | Brian |  | Closed | 150 | AM 7 |  | 8/8 - Proposed for AM 7 - 150 D estimate 8/11 - Chris to progress discussion with GP/TIAA first - then we will assess the need & timing with AM. 8/16 - Capacity Plan updated for 2016, AM6, this may be delivered early Feb 2017. 8/18 - Brian to determine in/out by 9/2 10/13 - hm: Mike and Brian going back to AM determine if they actually need it. Taking out of capacity plan.
2016-08-08 | 22 |  | Fractional shares in STAR Fractional Shares enhancement - AMMO originally created June 2009 - Identified by Operations as Critical for AM Oper Pilot | A | AM | Cheryl | Cheryl |  | Closed | 24 | AM-2016-10 |  | 8/8 - Proposed for AM4 8/11 - Need some additional definition in AMMO (Brian) 8/11 - Determine target delivery (Heather) 8/12 - Added to Master and Capacity Plan 10/24 - hm: Designated by Ops as required. 11/7 - MW: Moving this from Oct release to Nov release due to dev slip.
2016-08-08 | 23 |  | Resolve Star issues around coupons - Identified by Operations as Critical for AM Oper Pilot | A | AM | Cheryl | Cheryl |  | Closed | 24 | AM-2016-11 |  | 8/8 - Proposed for AM4 8/11 - Heather to determine target 8/12 Added to Master & capacity plan 10/12 - Closing, pending completion 10/24 - hm: Designated by Ops as required.
2016-08-08 | 24 |  | Performance Report Template - Missed in last Capacity Plan because # missing from "current estim" but was in MV/AM split columns | A | AM |  | Heather |  | Closed | 120 |  |  | 8/8 - Estimate added after 7/14 of 120 D not complete in line item 8/12 - Added to Capacity plan 08/08 control 8/12 - Closed 10/12 - This is changed in Master and Capacity plan putting to completion as it had not been closed previously.
2016-08-08 | 25 |  | Trade Partner Connectivity - Unclear what this is / where scope came from | A | AM | Heather | JoelD |  | Closed | 50 | AM-2016-12 |  | 8/8 - Proposed for AM 5 - No PRD / RMD / TRD 8/11 - Need Joel to define ASAP (Rasaan) 8/18 - Need Joel to estimate connectivity / testing support effort (Rasaan) 8/30 - Estimate is 50 Days totalv 30MV / 20AM. Joel will provide 1 PRD for each custodian. AM will require development work. 9/22 This my be just sending the trades to Sungard and QA. Add Sungard to title, IM work. There may be additional work per custodian. Rasaan to work with Justing and Joel to see if there is additional work 10/6 Inclued this topic in 10/11 discussion with AM team. 10/20 - hm: Need list of custodians and what needs to be implemented for trading with the custodians. 1/18 CLo MV to call custodians' API calls. We can close this for now until we get PRD from Joel.
2016-08-08 | 26 |  | Trade Bulk Cancel Phase 3 - Trade Recon Trade Bulk Cancel - Trade Recon (AM 4) - Increase result from RMD detail - Kendo vs Slickgrid | C | AM |  | Natalia |  | Closed | 35 | Consider |  | 8/8 RMD estimate is 35 days over PME estimate. Increase in scope of UI functionality (ability to sort) requires us to rewrite UI to use Kendogrid instead of slick grid (4 points). Need to confirm this is essential. 8/11 - Heather / Cheryl / Program Team to assess how to phase it and / or what other tradeoff can we make. 8/18 - Folded into Capacity plan 10/12 - Need to enter a Jira for Backlog. This is not approved for inclusion in 2016.
2016-08-09 | 27 |  | OFR-301 - set up encrypted IDs for DMA in 16.0 production - Late addition by GP | A | GP |  | Chris |  | Closed | 7 |  |  | 8/9 - Late request by TIAA - needed for their DMA go live 10/12 - hm: Completed for 16.1. Closing
2016-08-11 | 28 |  | (Not in Master) Northfield - Complete verification & testing / regression | B | AM | Mark | Brian |  | Closed |  |  |  | 8/11 - Work peroformed already - need to verify (Heather) 8/16 - Equities implemented ~1 year ago and in production. Will cost about 300K /year to get the mutual Fund and ETF data. The would need to implement solution. Brian would need to gather domain knowledgable folks to discuss how it should work in our system first. 8/25 - will have more directions after the meeting with AM in the week of 9/16. 11/1 - MW: Request Arlene to do a high level effort analysis. 1/18 CLo- per email from Mark: This agreement has progressed. Given that AssetMark has not yet concluded on rebalancing approach - integration of this new Northfield model may or may not be required for them. 1/19 CLo- next step: PM to prep for an EO/PRD. 1/19 CLo- per Brian, AM hasn't requested this feature. Closing for now.
2016-08-12 | 29 |  | Trade/Account Recon Rewrite Account recon rewrite | A | AM |  | Heather |  | Closed |  |  |  | 8/12 Added to AM5. Need PRD, PME. Is this already subsumed by Custodial EP for recon rewrite? 8/16 Added to AM 5. KevinR starting TRD to get estimate 9/15 Account rewrite requirements: performance improvements, get rid of socket.io emmory leak (account recon excaserbates the issue). With the replacement of socket.io and current definition of corporate action indicator this may be able to be delivered in later 2017. Unless performance not adequate for AM then needs to happen before go live. 9/23 - Struck through untill we determine this is necessary for AM. Estimate was 54 D. 10/6 - Two items replace socket.io removing successful positions from results. @Heather check with Kevin to document where rmoving successes is prevented. Still need backend rewrite, AMMO, @Heather to get AMMO from Kevin /Josh. 10/24 - hm: This was not accepted to add to AM scope. See above where the socket.io replacement will help with performance.
2016-08-16 | 30 |  | AM - Advisor-managed preferences | A | AM |  | Rasaan | Advisor | Closed |  | AM-2016-12 |  | 8/16 Advisor Managed preferences. Likely to move out to AM7 8/24 Moved to AM 7. Need to align with AM workstream. 8/24 Moved to AM 7, 2017 capacity plan 8/25 - Rasaan to provide more clarity 10/12 - hm: in Consideration state. Currently in capacity for 2016 10/20 - hm: In plan but PRD not complete till 11/15 so likely to slip 10/24 - hm: Closing no further action till we see a scope change
2016-08-16 | 31 |  | AM - Non custodial interfaces | A | AM |  | Rasaan |  | Closed |  |  |  | 8/16 Non custodial interfaces likely to move out to AM7. Need better definition 8/24 Moved from AM5 to AM 7 in Capacity plans 9/1 - Closed 10/12 - hm: Under consideration, not in capacity plan. 10/18 - Moved from Ops Apps to Ops Data (Brian) 10/20 - hm: PRD eta due 10/28
2016-08-17 | 32 |  | Convert and store historical transactions Create tool to import historic performance, market value and flows into Cassandra | B | AM |  | Arlene |  | Duplicate |  | AM-2017-01 |  | 8/17 - Per Brian, our existing tool loads data into Oracle and does not load market values or flows. Joe did an evaluation and determined that none of it was reusable. 8/25 - Arlene to talk with Joe/Kevin to create the TRD and get estimate. 10/25 - hm: Duplicate.
2016-08-17 | 33 |  | Sleeve Performance | A | AM |  | Brian |  | Closed | 0 | AM-2017-01 |  | 8/17 Customer pushing to have performance available for Sleeves. We ware investigating implementing Sleeve performance for Cash only. Arlene / KevinR starting TRD fr cash only to get an estimate. 8/24 Sleeve Performance for casho only PRD in review, needs to be discussed with customer. TRD to be in review next week. 8/25 our decision/recommendation is supporting performancefor cash across model. 9/15 Leaving open till Customer agrees 9/22 Customer agreed to proposed approach. No change to estimate at this time. 10/10 - I think this should be closed 10/12 - Open question as to whether this should be MV days. Mike let us know this ison us. 10/24 - hm- Per Mike billing is MyVest Contractual. Customer agreed to PRD 10/21.
2016-08-18 | 34 |  | AssetMark Security Classification | B | AM | Heather | Rob/David | Ops Data | Closed |  | Consider |  | 8/18 - We have a project to deliver a view of holdings by a custom AM classification. Unlcear if these days are captured anywhere or if they need to be added. 8/18 - Josh to look at if this is covered within Client Delivery. 8/25 - Shenba to write up the PRD. 10/20 bkm: Given this is security master data, I think it belongs to Ops Data. Will ask them for an EO. 10/20 - hm: AnnP and Kevin R preparing EO. Once we get we will add in Master. 10/21 - MW: Adding row for this project without estimates under "C-Consideration". Those will be filled in when EO complete. Need the record there for AM reporting. "AFR-51: AssetMark Security Classification" Was also suggested by BM that this is billable. 12/6 - hm: Waiting on AM. 1/18 CLo to check with Brian. 1/19 CLo- waiting for reqt's from AM. Closing this now and will track this project via AFR-51.
2016-08-23 | 35 |  | Updated TIAA Rebranding - PA QRP/P2P Changes owning program changed from Advisor to Operations Data | B | GP |  | Joanne |  | Closed |  |  |  | 8/23 - Line 44 on Master - OFR-275 was allocated to Advisor program team, but should be assigned to Operations Data as they own the QPR product. Shenba created the PRD - will Natalia own the requirements moving forward? 8/25 - to update SDLC Tracker Master and Capacity Plan 9/1 - Moved to closed.
2016-08-25 | 36 |  | AM4 - CRM PME Estimates - 50D, IEE - 80D | A | AM |  | Heather |  | Closed | 30 |  |  | 8/25 - Estimate 30 D higher than PME. and requested additional scope from AM for a phase 2 of ~30 D 9/8 - Master updated - in capacity plan 9/8 - Moved to Closed 10/12 - hm: Changed status to complete. This was delivered in AM4.
2016-08-26 | 37 |  | Provide success/response information on create Standing Instruction web service call. OFR-303 | A | GP | Brian | Heather |  | Duplicate |  |  |  | 8/26 - Brian: Waiting on GP to define if this should be bulk (provide URL) or single (provide success/failure); GP is asking that it be in the November DMA release. 9/19 - PME for OFR-303 has been approved. TIAA wants confirmation that this will be in the DMA release that occurs prior to November. 9/22 - Chris negotiating dates, suggesting swap for item in DMA 3. 9/27 - This is in DMA 3 and needs to be moved to Master (Brian). 10/6 - PME added to Master. It had been provided to GP but was reflected in SDLC. 10/12 - MW: Duplicate of other OFR-303 item
2016-08-31 | 38 |  | ADVUI UI Inv Portal UI EZ Button Advisor UI, EZ button, Investor Portal Reconciliation for 2017 detalied capacity plan | A | AM |  | Brian / Heather |  | Closed |  |  |  | 8/31 - Need to resolve the master record for breakdown of estimates for each of these items for details to be added to capacity plan. Assuming Matts detailed estimates are record for Advisor UI. Which column in in Josh/Brian's EZ butto spreadsheet is to be implemented first. Need to find record of estimates for investor portal. 8/31 Confusion about master records of details and estimates for Advisor UI, EZ Button, and Investor Portal requirements and priorities. Need to resolve for 2017 detailed plan. Documents that have information include: - Matts's detailed Advisor estimates https://docs.google.com/spreadsheets/d/1vo1t5Q6MzES8CnNCS_IJNkyQH4K6ORUOMfmSRSccYKw/edit#gid=1036275838 - Josh/Brian's Goal Based Proposal/Profile Feature list https://docs.google.com/spreadsheets/d/1LF4BVnB6CLW1uNQRLQz4aB2_fgMIymk9CTvrnb8wfT4/edit#gid=34285302 9/15 Brian updated SDLC with details and priorities. Heather Added to 2017 Capacity Plan. Team may alter priorities to reflect working on pages rather than wprking on components in page. 10/6 - Schedule time for review on Tuesday 10/11 | Matt's detail estimates
2016-09-01 | 39 |  | Convert and store historical transactions (Brian ?) Modify historical performance loader | A | AM | Brian | Heather | Ops Data | Closed | 30 | AM-2017-01 |  | 9/1 - Loader needs to be mofified to store data in Cassandra 9/22 - PME 4 points. Create RMD, leverage one time load. 9/27 - This is neede for conversion testing, so recommend that we move it to Master (Brian) 10/6 SDLC ended here 10/13 - hm: Must be done for AM. Not AM responsibility to pay for this, cost is because we moved performance to Cassandra. Heather update Master and Capacity, billing MyVest. 10/24 - In Master
2016-09-01 | 40 |  | OPM Phase 3 | A | AM | Brian |  | Advisor | Closed | 80 |  |  | 9/1 - Recalculation of alerts and other items that were deferred from original OPM project. 9/22 - Ideally they would have phase 2 for the pilot, but definitely for go live. 10/6 Need direction from Brian and this is currently not in plan on Master or Capacity 10/12 - hm: Brian, Justin, Heather discussed 10/10 and determined this is not necessary for AM. Putting this into backlog. till it is prioritized. Closing this item on the change control log.
2016-09-01 | 41 |  | 16.1.1 DMA patch 1 renamed DMA P1/16.1.1. | B | GP |  | Heather |  | Closed | 30 | 16.1.1 |  | 8/29 - Content for 16.1.1 (inclusive of DMA patch 1 and 16.1 roll overs) sent for review 8/30. Updates being made to SDLC Master and Capacity Plan. 9/15 Orig additional estimate +30. +60 due to bugs/changes from 16.1.
2016-09-02 | 42 |  | (Not in Master) Add liquidate functionality to PE | A | AM | Brian | Brian | IM | Closed |  |  |  | 9/2 - Open item from long ago when trading was moved from ISG to PE; required for AM workflows. 9/22 - Moved from ISG to PE lost functionality. Brian to do EO. Good candidate from contractor team if they have Flex experience. 10/20 - hm: May not be a requirement for launch. IM working on EO. Add to Consider 12/6 - hm: Agreed with Brian to close as AM has not asked for it yet.
2016-09-06 | 43 |  | (Not in Master) Contribution / Funding Alert | A | AM | Brian | Ann | Ops Data | Closed |  |  |  | 9/6 - Alert required for AM workflow that begins with a contribution 9/22 - AM Operational Pilot may require. Must be therefor readiness. We need PRD and EO. 10/20 - hm: Getting EOs then will discuss with AM steering committee. Add to Consider 1/18 CLo - to follow up with the AM team. 1/19 CLo- closed. AM hasn't yet approved.
2016-09-06 | 44 |  | (Not in Master) Hold Released Alert | A | AM | Brian | Ann | Ops Data | Closed |  |  |  | 9/6 - Alert required for AM workflow that kicks off when a hold is removed. 9/22 - AM Operational Pilot may require. Must be therefor readiness. We need PRD and EO. 10/20 - hm: Getting EOs then will discuss with AM steering committee. Add to Consider 1/18 CLo - to follow up with the AM team. 1/19 CLo- closed. AM hasn't yet approved. | PRD
2016-09-06 | 45 |  | (Not in Master) Model Drift Alert | A | AM | Brian | Shenba | Advisor | Closed |  |  |  | 9/6 - Alert required for AM workflow to track funding of a new account 9/22 - AM Operational Pilot may require. Must be therefor readiness. We need PRD and EO. 10/20 - hm: Getting EOs then will discuss with AM steering committee. Add to Consider 1/18 CLo - to follow up with the AM team. 1/19 CLo- closed. AM hasn't yet approved.
2016-09-07 | 46 |  | Access Billing Integration Remove access billing | A | AM | Heather | Brian/Justin | Ops Data | Closed | -25 | AM 5 |  | 9/7 - Remove Access Billing 10/11 - Descoped from SDLC and Capacity Plan.
2016-09-07 | 47 |  | (Not in Master) Link SMAs to Models | A | AM | Brian | JM | IM | Closed |  |  |  | 9/7 - Historically, we have done this through the UI but I think the volume of SMAs used by AM will require a web service 10/13 - hm - SMAs to model is done by hand today. Need add back into plan to determine how to automate , PM to work on EO. 10/20 - hm: Getting EOs then will discuss with AM steering committee. Add to Consider 12/6 - hm: Added to consider. JM needs to provide PME
2016-09-08 | 48 |  | OFR-303 - New Web Service for Standing Instructions | A | GP | John | Brian | IM | Duplicate |  |  |  | 9/9 - TIAA requested this be in DMA 1.3 (they need it in November) 9/22 - Duplicate of "Provide success/response information on create Standing Instruction web service call" 10/4 - Capacity plan and Master updated 10/10 - I think this should be closed 10/12 - MW: This is a duplicate of the other OFR-303 item.
2016-09-12 | 49 |  | Tax Shield report estimate decrease | A | AM | Brian | Heather | IM | Closed | -87 | ADVUI-2017-03 |  | 9/12 - Matt assessed the remaining work and scoped it as 6 points. Created IEE for that value 10/12 - hm: Changes reflected in Master and 2017 capacity plan. 10/20 bkm: I think we can close this.
2016-09-12 | 50 |  | Response messages for duplicate web service calls (OFR-300) | A | GP | Brian | Chris | Advisor | Closed |  |  |  | 9/12 - GP approved the PME and is asking for the PRD but it doesn't seem that this project is scheduled for a release yet. 9/13 - TIAA is asking if we can add this to release 16.1.3 and move out OFR-295 and OFR-296. This is a net +12 days for Advisor 9/22 - Replace OFRs 295&296 with 303. Web services that may be done by other teams. Target Jan 10/6 - MWW: Duplicate of item below "Remove OFR295 and OFR296".
2016-09-13 | 51 |  | Request that AssetMark Day 1 and Day 2 epics created for both Ops Apps and Ops Data be added to the SDLC for tracking and resource planning. | A | AM | Natalia |  | Ops Data / Ops Apps | Duplicate |  |  |  | 9/13 - Currently there are epics created for both Operations programs (Data Day 1: AMMO-44105, Day 2: AMMO-44106. Applications Day 1: 44107, Day 2: AMMO-44108) which house numerous one-off AMMOs that Cheryl has identified as needed for AssetMark. I would like to add these epics to the SDLC for resource planning purposes. Two of the Ops Applications Day 1 AMMOs are listed on the SDLC currently (lines 47, 48) and I would like to replace these with the overarching epic. 9/22 - Ops Apps to bundle and fix as project. Joanne checking with Ops Data on plan.
2016-09-13 | 52 |  | Port existing Investor Portal pages to Pages | B | AM | Brian |  | Advisor | Closed |  |  |  | 9/13 - In speaking with Victor it came up that there is work required to migrate the existing pages to Pages framework 10/4 I'm assuming that work is contained in SPSinvestor portal UI work for 2017, currently 160 days. Does this work?
2016-09-14 | 53 |  | Request to link/slot AFR-21 (Link Multiple Groups of Portfolios in a Household) to the AM QPR project in AM6. |  | AM | Natalia |  | Ops Data | Duplicate | 0 |  |  | 9/14: We haven't received client sign off or feedback on the PRD for AFR-21 and since it relies on the QPR so heavily I think it makes sense to do this work alongside actually building the QPR. 9/22 Dup
2016-09-14 | 54 |  | Trade Bulk Cancel Phase 1 - Trade Recon Scope change: Trade Bulk Cancel Phase 1 - Trade Recon | A | AM | Scott |  | Ops Apps | Closed | -23 | AM-2016-10 |  | 9/13: Approved RMD is actually for 42 days, down from 65.
2016-09-14 | 55 |  | Trade Bulk Cancel Phase 2 - Trade Recon Scope change: Trade Bulk Cancel Phase 3 - Trade Recon (better name suggestion: Kendo Conversion and Enhanced Active Search) | A | AM | Scott |  | Ops Apps | Closed | 48 | AM-2016-10 |  | 9/13: Proposed 12 SP. Change is from original (Points moved out of Phase 1: 65-42=23) to final Phase 2 points (71). Convert to Kendo, use nested grids instead of master/slave, and implement filtered criteria in Active Search - applied to make consistent across Trade Recon, Account Recon, and transaction Manager. Move Summary enhancements to phase 3. 9/22 If all functionality in Phase 1 move out 2. 10/7 Moved Phase 2 to AM-2016-10 release 10/24 - hm: Total scope increase of 25D due to MyVest Technical debt.
2016-09-14 | 56 |  | New project: Trade Bulk Cancel Phase 3 - Trade Recon (better name suggestion: Summary Enhancements) | B | AM | Scott |  | Ops Apps | Closed | 29 |  |  | 9/14: Tentative 5 SP. Summary enhancements - applied to make consistent Trade Recon, Account Recon, and Transaction Manager. If we want to include UX redesign the estimate will increase.
2016-09-16 | 57 |  | Remove/Merge Access Billing Integration (line 51) with the Data Mart project | A | AM | Natalia | Brian | Ops Data | Duplicate |  |  |  | 9/16: My understanding is that this work has been merged into the data mart project 10/4 Put DataMart in front of line item and left in December deliverable. 10/6 Reopening, need Cheryl, Arlene, Brian to verify.
2016-09-16 | 58 |  | Link Multiple Groups of Portfolios in a Household Move Ability to link multiple groups of Potfolios in a household to combine with QPR | A | AM | Heather | Natalia | Ops Data | Closed |  | AM-2017-02 |  | 9/16 Move Ability to link multiple groups of Potfolios in a household to combine with QPR (Brian move to where?) 9/22 - Move to align development of the QPRs. 10/4 - Capacity plan and Master updated and moved to AM-2017-2, Rasaan received info 10/24 - hm: Moved to same release of personalized QPR
2016-09-16 | 59 |  | Custodial Endpoint Lots PRD-RMD breakdown change | A | AM | Frederic |  | Ops Data | Closed | 0 |  |  | 9/16: The 'Custodial Endpoints - Open & Closed Lots' SDLC project (IEE 27) has been broken down into two RMDs, one for Open Lots (AMMO-41668, IEE 7) & a second for Closed Lots (AMMO-46260, IEE 20). Also the Closed Lots release needs to be pushed out to the AM-November date or later.
2016-09-19 | 60 |  | PA Proposal Enhancements - SMA Indicator Box Remove OFR-231 from release 16.2 | A | GP | Chris |  | Advisor | Closed | -9 | 16.2 |  | 9/20 - TIAA confirmed that this will not be necessary for 16.2 10/4 Removed from capacity plan and Master
2016-09-20 | 61 |  | AMMO-45171 - Remove Alert Management Role in AM Advisor Role | A | AM | Sajid |  | Advisor | Closed | 2 | AM5 |  | 9/20 Sajid: Revert the changes to the PCC Advisor Overview page made for the AssetMark Trade Training demo and implement the solution the right way 9/22 - Is this just a bug. Completing 10/10 - Scope change less than 10 days. Was 2 day estimate.
2016-09-20 | 62 |  | (Not in Master) Exclude from Startegy Personalization PCAP-15 | B | PCAP | John | Chris | IM | Closed |  |  |  | John EO Target Date 9/23 10/25 - hm: What is the request, to add this to the PCAP 16.1 release in December? 10/25 - jm: These have been requested via Rasaan for a future release not specified, and not for PCAP 16.1. Please put into Consider 10/26 - hm: Need an EO 10/26 - jm: EO is 2.5 pts/15 days. I have socialized this internally but do not know what has been communicated to Personal Capital 11/1 - hm: ChrisF, Does PCAP want this for a 2017 release? Confirmed with JM this is not for 2016. 11/21 - pcap would like this feature in an early 2017 patch if possible 12/9 - customer requested to include in 16.3 release 12/12 - will be included in 16.3.1 2017Q2 1/18 CLo- this will go in to 16.3.1.2.
2016-09-20 | 63 |  | (Not in Master) TOB - Allow cancellation of open orders PCAP-16 | B | PCAP | John | Chris | IM | Closed |  |  |  | John EO Target Date 9/23 10/25 - hm: What is the request, to add this to the PCAP 16.1 release in December? 10/25 - jm: These have been requested via Rasaan for a future release not specified, and not for PCAP 16.1. Please put into Consider 10/26 - hm: Need an EO 10/26 - jm: EO is 9 pts/54 days. I have socialized this internally but do not know what has been communicated to Personal Capital 11/1 - hm: ChrisF, Does PCAP want this for a 2017 release? Confirmed with JM this is not for 2016. 1/18 CLo to check with Rasaan. 1/19 CLo- per Rasaan, PCAP does not have plans to move forward with this. Closing.
2016-09-21 | 64 |  | Dividend Accrual Treatment - performance calc | A | AM | Frederic |  | Ops Data | Closed |  | AM-2016-11 |  | 09/21: the 09/13 RMD completion date will be pushed out. Update will be provided next week. Technical design to be confirmed with potentially significant impact to effort required. 10/25 - hm: Moved to Novemver release
2016-09-21 | 65 |  | Move 'Project to calculate/match realized gain/loss per transaction' below Custodial Endpoints (Closed) Lots | B | AM | Frederic |  | Ops Data | Closed | 0 |  |  | 9/21: This project needs to be after the Custodial Endpoints Closed Lots project (see 09/16/2016 entry above). This report uses the Closed Lots data. The delivery date needs to be pushed out per the Closed Lots project completion change.
2016-09-22 | 66 |  | Trade Bulk Cancel Phase 2 - Trade Recon Trade Bulk cancel prioritization over Corporate Action Indicator | A | AM | Scott |  | Ops Apps | Closed | 0 | AM-2016-10 |  | 9/22 - Update SDLC to reflect that at the start of AM4, stakeholders (Engineering, Product, Cheryl) agreed that Trade Recon Bulk Cancel would take priority over Account Recon Corporate Action Indicator and given resource constraints we'd need to request a move of the latter to AM5 or later. 10/4 Complete
2016-09-22 | 67 |  | Post-processing to correct for penny differences caused by STAR posting of COUPON payments | X | AM | Justin |  |  | Closed |  |  |  | 10/6: MWW - What is the Action? Is this a proposed scope change - if so it should be documented in an AMMO with the effort impact summarized here please.
2016-09-22 | 68 |  | Enhancements to recon process for Pending Re-orgs | X | AM | Justin |  |  | Closed |  |  |  | 10/6: MWW - What is the Action? Is this a proposed scope change - if so it should be documented in an AMMO with the effort impact summarized here please.
2016-09-22 | 69 |  | Automation of cancel/correction processing for TRADES | X | AM | Justin |  |  | Closed |  |  |  | 10/6: MWW - What is the Action? Is this a proposed scope change - if so it should be documented in an AMMO with the effort impact summarized here please.
2016-09-22 | 70 |  | Improved support for cancel/correction processing for NON-TRADES | X | AM | Justin |  |  | Closed |  |  |  | 10/6: MWW - What is the Action? Is this a proposed scope change - if so it should be documented in an AMMO with the effort impact summarized here please.
2016-09-22 | 71 |  | Support for COS (intra-account journals -- if we decide to do anything for this) | X | AM | Justin |  |  | Closed |  |  |  | 10/6: MWW - What is the Action? Is this a proposed scope change - if so it should be documented in an AMMO with the effort impact summarized here please.
2016-09-22 | 72 |  | Remove OFR295 and OFR-296 from 16.1.3 and add OFR-303. | A | GP | Chris | Heather |  | Closed | -12 | 16.1.3 |  | 9/22 - Genpact would like to add OFR-303 for 16.1.3 and remove OFR-295 and OFR-296 10/4 - Chris - Took out OFRs 295 / 296. Added OFR303. The notes in the OFR state they want OFR 300 also. Is this the case? Note from Chris they would like 300but he told them no unless they want to move the date. They declined to move the date.
2016-09-22 | 73 |  | Rename Automatic Tax lot load for PAM and PA to Automated Funding for PA | A | GP | Ann |  |  | Closed |  |  |  | 9/22 - Possibly remove from 16.2 as it requires regression testing (confirm with Chris Flynn)
2016-09-23 | 74 |  | Trade Netting Block Level Trade Netting Scope Increase | A | AM | Heather | Brian | IM | Closed | 13 | AM-2016-10 |  | 9/23 - PME was 70, RMD estimate is 83. RMD not signed off on yet. 10/14 - hm: Requirements have changed.This will require client sign off. Meeting with AM set for 10/14. PRD and RMD completion pending on the clarifications from the meeting.Need to add change control entry for target date update to 11/8. 10/20 - hm: JM review one last open change, expected 10/27 10/24 - hm: Eng implemented as much as it could. Waiting on client. Released to UAT. 11/2 - bkm: Still waiting on client for feedback. Client needs to sign off on PRD. 12/6 - hm: Closing as we will ship what has been implemented. Any additional functionality will have to go through change control.
2016-09-23 | 75 |  | OFR-297 New edit fee schedule web service | A | GP | Joanne |  |  | Closed | 6 |  |  | 9/23 - PME was 6, RMD estimate is 12. Increase due to additional complexity for testing external web service.
2016-09-27 | 76 |  | Bulk Rebalance Phase 2 | B | AM | ? | ? | IM | Closed |  | AM-2016-10 |  | 9/27 Team is working for code complete 10/11. Contingent upon getting an environment for volume testing between 10/3 to 10/7
2016-09-27 | 77 |  | AFR-13 Strategy & Model Change Alert Phase 2 candidates | A | AM | Sajid | Brian M. | Advisor | Closed | 7 | AM4 |  | 9/27 SM: There are about 8 items, mostly feature enhancements coming out of demos plus a couple of tech improvements. 10/3 SM: Decided with Brian M to build only the items that were in the original scope. Plus included small tech debt items - total of 2.5 points (about 7 days). The remaining items will be considered for a future release. 10/4 - Less than 10 days so no change to capacity, using OPC time to cover. 10/12- hm: Changed status to complete, delivered and less than 10 days so did not need a line item in change control.
2016-09-27 | 78 |  | Clean up Custodial EP entries in SDLC for correctness | A | AM | Heather | Heather |  | Closed
2016-09-27 | 79 |  | (Not in Master) Add OFR-300 to 16.1.3, now known as 16.2.1 | A | GP | Chris | Heather |  | Closed | 0 | 16.2.1 |  | 9/27 - TIAA has asked if we can accommodate OFR-300 in 16.1.3. They are not expecting it, but if we have capacity and need DR days, can we consider? 10/4 - See add of ofr-303. Client declined to move date so closing this request. (42D for 300). 10/24 - Does not exist in Master.
2016-09-27 | 80 |  | SDE and other reports sent to FTP Remove OFR-264 from release 16.2 | A | GP | Chris |  |  | Closed | -24 | 16.2 |  | 9/27 - Genpact/TIAA confirmed that this is no longer a 16.2 feature 10/4 - Removed at client request 10/10 Master and Capacity plan updated
2016-09-28 | 81 |  | (Not in Master) DMA Parallel work unit execution | B | GP | Prakash | Prakash | ON | Closed |  | 16.2 |  | 9/22 -DMA workunits need to be spread across schedulers and tested. 10/25 - hm: Needs an EO. 1/18 CLo: Checked with Prakash. The work is largely done but we still need to create test cases. Heather has asked Prakash to provide estimates on the remaining work. 1/20 CLo- closing as the remaining work ahs no impact on Capacity Model.
2016-09-28 | 82 |  | Enable Ops Performance Server in GPI | X | GP | Chris | ? | Ops Data | Closed |  |  |  | Need Ops Server enabled in GPI integration to prepare to turn CP Performance on
2016-09-28 | 83 |  | Align 16.1.2 and 16.1.3 dates with sprint end dates | A | GP | Chris |  |  | Closed |  | 16.1.2/16.1.3 |  | 9/28 - Dev complete for 16.1.2 is currently set for 10/28. Request to move the date up to 10/25 to coincide with the end of a sprint. We will turn the environment over to the customer for testing on 10/27. Dev complete for 16.1.3 is currently 12/30. Request to move this date out to 1/3/17 to coincide with the end of a sprint. We will turn the environment over to the customer for testin on 1/5/17
2016-09-28 | 84 |  | Enable CP Performance in GPI | X | GP | Chris |  | Ops Data | Closed |  |  |  | Need CP performance enabled in GPI for Genpact testing
2016-09-29 | 85 |  | Rename "Corporate Action Indicator - Account Recon" to "Account Recon Improvements" | B | AM | Scott |  | Ops Apps | Closed |  |  |  | 9/29 - Product has always called this project Account Recon Improvements in PRD. It's misleading to call it Corporate Action Indicator because 1) it includes changes for smarter display of failures and improving logic for factored securities and 2) we're only going to use indicator for stock splits.
2016-09-30 | 86 |  | Determine process to load portfolio level strategy / model change | X | AM | Justin |  |  | Closed |  |  |  | Used for the AssetMark Market Value vs Net investment over time graph
2016-09-30 | 87 |  | CP Proposal and QPR Changes for Sandbox Request to add OFR-288 to release 16.2 | A | GP | Chris | Heather |  | Closed | 36 | 16.2 |  | The PME approval for OFR- CP Sandbox #3 came in late. Hoever TIAA is asking if we can accommodate as this is a key component of CP. it is a 36 day project 10/4 - Master and Capacity updated 10/10 - Pending completion 10/12 - Currently, the master spreadsheet has one line item for Ops Data but both the Advisor team and Ops data team need to work on it. Please add another line item for the advisor team. 10/18 - I noticed that there are two line items (one Ops Data and one Advisor) so I think this can be closed (bkm) 10/24 - Brian what is the estimate for this per team.
2016-09-30 | 88 |  | MAFS Fee Project Phase 3 Remove OFR-270 from release 16.2 | A | GP | Chris | Heather |  | Closed | -46 | 16.2 |  | OFR-270 - MAFS Fees phase 3, is offically out of the release 10/4 - Master and Capacity updated 10/6 @Heather add scope change 10/10 - Scope impact added
2016-09-30 | 89 |  | Automatic Tax lot load for PAM and PA Remove OFR-259 from release 16.2 | A | GP | Chris | Heather |  | Closed | -18 | 16.2 |  | OFR-259 - automatic tax lot load, is offically out of the release 10/4 Assuming this is 16.2. Master and Capacity updated 10/6 @Heather add scope change 10/10 -Pending completion
2016-10-03 | 90 |  | Deletion of Personalization Changes to deletion of Personalization from the Advisor UI pages | B | GP | Shenba | Brian | Advisor | Closed |  | 16.2 |  | Meeting scheduled to discuss the requirements 10/20: hm - PRD should be ready. Need to assess if this fits into 16.2 AMMO-46918 (Epic) 10/21- hm: Added to Master need to get IEE 11/1 - hm: Confirm with Frederic no work for Ops Data 1/18 CLo - going in to 16.2.0.3.
2016-10-04 | 91 |  | SMI Model Change Impact Web Service update | X | AM | Namrata |  |  | Closed |  |  |  | 10/4 New Target date 10/25 with QA complete
2016-10-04 | 92 |  | Targeted Rebalance Update | X | AM | Namrata |  |  | Closed |  |  |  | 10/4 New Target date of 11/8 QA complete. PRD changed based on review discussions.
2016-10-04 | 93 |  | Trade Netting | X | AM | Namrata |  |  | Closed |  |  |  | 10/4 New Target date of 11/8 QA complete
2016-10-04 | 94 |  | CDA Withdrawl Request update | X | AM | Namrata |  |  | Closed |  |  |  | 10/4 New target date of 11/25 QA complete
2016-10-04 | 95 |  | Open Order Deletion Date update | A | GP | Namrata | ? |  | Closed | 50 |  |  | 10/4 Requirements changed based on Ops recommendation.Based on that new RMD is being created.Original target completion (dev&qa) is 10/25
2016-10-05 | 96 |  | Multiple withdrawal match for Standing Instruction | A | AM | John | Brian | TBD | Closed | ? | AM-2016-11 |  | Is currently assigned to Inv Mgmt but this may have been due to bandwidth at the time this was created
2016-10-06 | 97 |  | Item on Master called "Advisor View" - unclear what this is - no estimates | A | AM | Mark | Brian |  | Closed |  |  |  | 10/6: Brian - please look at this and determine if it is really a scop item.
2016-10-06 | 98 |  | Corporate Action Indicator | A | AM | Heather (Scott) | Heather |  | Closed |  |  |  | 10/6 PGM Lead forgot to call out still in RMD phase and will not make AM-2016-10. Trade Bulk Cancel Phase 2 brought in to AM-2016-10 from November release instead.
2016-10-10 | 99 |  | HH Overview AM - Advisor UI - Overview - This project / feature is not in scope or EOs | A | AM | Mark | Brian | ADV | Closed | 132 |  |  | 10/10 - MW: There was no estimate for this and there does not appear to be any scope deifinition or EO. Moving to descoped to take it out of the project list. 10/20: BKM: The HH Overview project is currently being worked on but was moved to Descoped in SDLC; need to move back to active project. 10/24 - hm: Added to Master. PME of 80 D is being re-evaluated. PME is now 132 D. Heather should recoprt what impact of adding would be at SDLC 10/27.
2016-10-10 | 100 |  | Transaction Manager - Passthrough/Custodian Mapping looks to be duplicate of Transaction Manager - Passthrough/Custodian Phase 2 | C | AM | Mark | Chris |  | Closed |  |  |  | 10/10 - MW: Are these duplicate? Dates and estimates all look identical. 10/24 - hm: Chris where are these in Harvest? Delivered in AM2 and AM3
2016-10-10 | 101 |  | AM Projects that have a AM/MV split - Split these into 2 rows for tracking purposes - Cust & MV days are highlighted | A | AM | Mark | Mark |  | Closed |  | AM |  | 10/10 - Rows that have shared budget for AM are now split into two rows with Highlight on the Cust vs MV days.
2016-10-10 | 102 |  | Corporate Action Indicator - Account Recon |  | AM | Scott |  | Ops Apps | Closed | 76 | AM-2016-11 |  | 10/10 - RMD estimate (IEE) is 59 10/13 - (added in RMD Spent) RMD estimate (IEE) is 76. RMD Actual: 10/12/2016 10/24 - hm: Also known as Account Recon Improvements 10/25 - hm: Unplanned, 76 days. In Master and Capacity Plan.
2016-10-10 | 103 |  | Split work for Sanbox #3 into two line items: work for Ops Data and work for Advisor | A | GP | Ann |  | Advisor | Closed |  |  |  | 10/10/16: https://jira.myvest.com:8443/browse/OFR-288 has work for two teams: Ops Data and Advisor. Please split the single line item for this feature into two, one for each program.
2016-10-11 | 104 |  | Future dated trades for CRT - on demand rebalance - Need to verify cust acknowledged scope | A | AM | Mark | Mike |  | Closed | 150 |  |  | 10/11 - MW: Brian or Mike need to verify if this is necessary then we need to assess if the estimate is correct. 10/20 - hm: Brian states AM does not need Future Dated Trades. Need to document work around in user guide. 10/27 - MW: Classified this as Descoped.
2016-10-11 | 105 |  | (Not in Master) Dedicated Dev Support for Data Conversion | A | AM | Rob |  |  | Closed | 20 |  |  | 10/11 Added issue. We are asking for 1 person for Oct. 10/13 - hm: Conversion for AM was part of orignal estimates for AM, Data Conversion 325D, non strategic, billable full rate. Need to add to Master and Capacity Plan.
2016-10-11 | 106 |  | (Not in Master) Dedicated Dev Support for Operational Pilot | A | AM | Rob |  |  | Closed | 20 |  |  | 10/11 Added issue. We are asking for 1 person for Nov. 10/13 - hm: see Dedicated Dev Support for Operational Pilot. 12/6 - hm: Closing as we have been supporting them.
2016-10-11 | 107 |  | CP Proposal and QPR Changes for Sandbox | B | GP | Frederic | Chris | Ops Data | Closed | 6 | 16.2 |  | 10/11 Added issue. OFR-273 & OFR-288 should be implemented against the latest PDF framework version. Otherwise supporting the graph features requested increases significantly (approx 20 days) and supporting such code could be costly. However using updated PDF frameworks requires a full regression test on QPRs. 10/13 - hm: Feature, make asset allocation in QPRs dynamic, grew from 2 pts to 5 pts. Chris is going to negotiate with the customer. 10/14 - hm: Added CP Proposal and QPR Changes for Sandbox to Master and Capacity 10/19 - hm: OFR-288 New EO is now at 8 points, 21 D fr Ops Data, 21 D for Adv 10/19 - bkm: For OFR-288 the Ops Data work will not make 16.2 release; needs to be scheduled for another release. 10/25 - hm: Verify the Impact scope with Brian, EO and Sajid IEE. 11/1 - hm: Descoping Ops Data work for 16.2. Master and Capacity Plan updated.
2016-10-12 | 108 | Need JIRA | (Not in Master) Handle rejects in Trade Order Blotter (TOB) | A | MV | Brian | CLo | IM | Open | 74 |  |  | 10/12 - We never implemented a mechanism to handle rejects of orders or allocations, which will likely be problematic for AM 10/25 - hm: Need an EO and Pgm Teaam. 1/26/1 CLo- i searched in AFR but did not find this one. Need to double-check with the AM field team and add this to AFR if needed. 2/9 RG: Unclear that this should have an AFR. Is this a "BLT" item? What is "TOB"? Also, why does this need an EO if Scope Impact indicates 74 days? 2/13 CLo- Brian let me know there may be an AMMO in IM's backlog for this one. Next step: CLo to talk with JohnM to get this prioritized and estiamted.
2016-10-12 | 109 |  | HH Overview ADVUI - Overview |  | AM | Joanne | Brian | Advisor | Duplicate | 80+ |  |  | 10/12 - Questions on missing features for AdvisorUI and Investor Portal in the SDLC - requesting PM update 10/13 - hm: Overview was found to be missing from Master, 80D. This is not on th Master or in the capacity plan. Team is working on this and we will add to Master and Capacity. Shenba to compare her inventory to Master.
2016-10-12 | 110 |  | Income Sweep Reserve AFR-4 - confirm appropriate Program | A | AM | John | Brian | IM | Closed | 0 | AM-2017-02 |  | In discussing w/ Dan and Namrata, the Advisor team might be more appropriate to assume responsibility for this. Matt has reviewed and has a few questions related to the project. 10/12 - hm: Did the name change from Principal & Income to Income Sweep Reserve? JM confirmed 10/13 - hm - Arlene confirms this is Ops Data. IM should have a test that min cash, personalizations work. Brian to determine if this is over ridable. Then ADV work likely. 10/26 - bkm: No need for AM to do any override work. 11/2 - hm: Closing
2016-10-13 | 111 |  | (Not in Master) Read Model web service | A | AM | Brian | JM | IM | Closed |  |  |  | 10/13 - We have a read strategy web service but not a read model web service. 10/20 - hm: Getting EOs then will discuss with AM steering committee. Add to Consider 10/26 - jm: seems like a logical addition but this has not come up in any of the SMI discussions and it seems like we are proposing to AM, they are not requesting from us 12/6 - hm: This is new read web services. PM is JM, need PRD and PME. 1/18 CLo to check with the AM team. 1/19 CLo- this is now tracked via AFR-146. Closing.
2016-10-13 | 112 |  | Prudential Integration descoped on Master |  | AM | Heather | Joel | Ops Data | Closed | -45 | AM 7 |  | 10/13 - hm: Prudential descoped on Master and no entry in change control log. Joel is this descoped? Yes.
2016-10-14 | 113 |  | SMI Model Change Impact Web Service |  | AM | Heather | Heather | IM | Closed | 12 | AM-2016-10 |  | 10/14 - hm: Scope impact due to need to create new web service / refactor existing code. The existing code is not a service and has bugs. 10/24 - hm: Mark adding additional row to Master to track the umplanned work.
2016-10-14 | 114 |  | Custodial Endpoints - Open Lots Custodial Endpoints - Closed Lots Custodial Endoints Open & Cloed Lots |  | AM | Heather | Heather | IM | Closed | 76 | AM-2016-10 AM-2016-11 |  | Breaking Open and Closed lots into 2 line items 10/24 -hm: Broken into 2 line items. Actual fr Open Lots IEE was 27D. IEE for Closed Lots is 49D.
2016-10-14 | 115 |  | Write Qeries to the Data Mart | [5 empty] | Closed | -30 |  |  | 10/14 - hm: Descoped as Views are part of data mart work
2016-10-19 | 116 |  | Open Order Deletion - page - Ops console Open Order Deletion Date update |  | AM | Namrata | John | In Mgmt | Closed | 26 | AM-2016-11 |  | This project will be feature complete by Oct 28 (team members pulled from Trade Netting to start on it this sprint).Requesting to move it to Nov AM release. 10/24 - hm: Scope Impact updated, in Master and Capacity plan 10/25 - hm: Reopned. Scope went from +24D to +50D. Brian to review with PM. 12/6 - hm: This is in AM-2016-12, Closing.
2016-10-19 | 117 |  | View a terminated account 180 days after closure | A | AM | Scott | Schenba | Ops Apps | Closed |  | AM-2016-11 |  | 10/19: Propose splitting project into two phases. <Phase 1> Ops Apps: Change Eagle messaging to fail posting if account terminated (2 story points); Ops Data: Restrict loading and/or mark positions and transactions according to availability timeline (1 story point) <Phase 2> Advisor: Change Advisor UI to view terminated account info, add field, and toggle viewing (TBD story points). Story points are much less than initial estimate because we realized we don't need to create a new account type, create and link to new terminated account of that type, and transfer time-series data from original account to new terminated account. 10/27 - hm: Rob does the customer have expectations as to when they will get this. If so move to Q1 2017 timeframe. 11/11 - rg: They were expecting to see this 11/23, but now they are not because we have communicated that this will be in Q1 2017 timeframe.
2016-10-20 | 118 | Need JIRA | (Not in Master) Account Recon Enhancement Account Recon will need new functionality | A | AM | Arlene | Justin | Ops Data | AM Cancelled |  |  |  | 10/20 - hm: Need logic to match custodian transaction with standing instructions. Add to multiple inst in Master. AM record as a scope item and need requirements. 10/24 - Is it a miss and or billable? What is the estimate? Once we have that info we'll determine whether to add to plan. 1/18 CLo to check with the AM team. 1/27 CLo- Spoke to Justin. Next step: Justin to check with Ops Data to see whether it's already done.
2016-10-20 | 119 | N/A | (Not in Master) Request to include GP Recon OPCs into the reconciliation work we are doing for AssetMark. These are deferred UATs from the 15.2 release. | B | AM | Chris | Rob/David | Ops Apps | AM Cancelled |  | 17 |  | 10/20 - We have a number of outstanding UATs from the recon re-write in 15.2. Can we look into addressing these with the work we are doing for AM? 10/25 - hm: What is the list of Jiras and what is the combined EO. 10/27 - cf: OPCs: 7174, 6590, 6636, 6591, 6602, 7164, 7206, 7208, 7219, 7011. I don't think we have an EO on these items. These were UATs they filed with 15.2 that we deferred and have never resolved. Should we/can we work these items into the work we doing for recon? Or evaluate them to se if they are still isues? 1/10 - check with Heather/Chris. 2/9 hm: What is the EO? 2/10 CLo- Rob/David, can you please prioritize this one on to the "to be EO'ed" list?
2016-10-20 | 120 |  | CRM Team Creation Web Service Team Creation Web Service | A | AM | Justin | Justin | PE | Closed | 27 | Await Approval |  | 10/20 - hm: Added for Justin. Need to add team web services early. "Move Team Creation WS (CRM v2) to as soon as possible in dev plan" 10/24 - hm: Asset Mark CRM needs an additional webservice for Team add, update entered for Consider 10/27 - hm: Mike to put this in front of AM for cost consideration. 11/8 - rg: per Justin this is in scope. Please proceed to add to dev plan / release schedule / sprint pipeline etc. 12/6 - hm: Added and being delivered in AM-2016-12
2016-10-20 | 121 |  | Optimizer Rebalance Enhancements PCCAP Optimizer estimates | A | PCAP | Heather | Brian | IM | Closed |  | PCAP 16.1 |  | 10/20: hm - Are these EOs complete?
2016-10-21 | 122 | AFR-88 | AFR-88 Model Diaplay Name / change web service integration - add scope Add a change request to the SMI integration project for the db change and web service updates. | A | AM | Justin | Rob/David | IM | AM Cancelled | 15 | Consider |  | 10/20 - hm: Work with IM and ADV to add these changes to this project. 10/24 - hm: services delivered with AM4. Need to go back and add a display name to these services. Mark adding to the consider list, not added to capacity. Need an EO 1/27 CLo- Confirmed with JohnM. This item is now tracked via AFR-88. Waiting for AM to approve EO/PME.
2016-10-21 | 123 |  | Bank Holiday Support (multiple calendars) | C | AM | Natalia | Heather | Ops Data | Closed | 75 | AM-2017-02 |  | 10/21: Request to reassign line item 65 to Ops Data - creation of business calendars in Eagle should fall in the Ops Data domain, not Ops Apps
2016-10-21 | 124 |  | (Not in Master) Create rebalance method of Standard with SI and model change; update create portfolio web service | A | AM | Brian | John | IM | Closed |  |  |  | 10/21 bkm - AM will be using a rebalance mode that is manual but automatically rebalances on model change and for withdrawals. We currently only support model change OR withdrawal as an event to rebalance. IM program doing an EO. 10/24 - Is it a miss and or billable? What is th estimate? Once we have that info we'll determine whether to add to plan. 10/27 - hm: Brian has the action to determine if this is part of AFR-29 11/15 bkm: Waiting on AM to confirm this is needed 12/6 - hm: Closing as AM has not confirmed this is needed.
2016-10-22 | 125 | AFR-7 and ADVUI | (Not in Master) Add use cases/features to the advisor UI and AM QPR projects to define which pages/dropdowns should use display name on the model table. | B | AM | Justin | CLo | ADV | Closed | 6 |  |  | 10/20 - hm: Work with IM and ADV to add these changes to this project. 10/25 - hm: Need page items. Is the 6 days the EO? (Brian) 1/27 CLo- spoke with Justin. Need to check with the PM team to see whether the requirements are already tracked. 2/2 CLo- check with the PM team. We now have this req't tracked in two places for ADV UI and QPR (Ops App): 1) For ADVUI: Comment from Shenba in email thread 2/2/2017: Thanks Justin. The only place that I can think of where we use the model name in the Advisor UI (Phase 1) is Sleeve Performance selection. I'll change the user stories for that page to show "model display name" instead of model name. 2) For QPR: per PMs' request, I added Justin's comment to AFR-7 (QPR) so that Natalia can add it to the PRD. Closing this item in Change Log.
2016-10-24 | 126 |  | Provide Fee Discount feature Bug fixes Opps App - Project consolidation | B | PCAP | Scott | Heather | Ops Apps | Closed |  |  |  | 10/24 - sa: "Provide Fee Discount feature" is listed as the sole item Ops Apps will do in the "Proposed PCAP 2016 Release" sheet, which is separately captured in the "Bug fixes Opps App" project. I propose removing the "Bug fixes Opps App" project and promoting "Provide Fee Discount feature" to Planned. 1/19 CLo- caught up with Scott. We have two lines in Master representing this work. Need to delete one of them make sure the other one is up to date and properly reflected in the Capacity Plan. 1/26 CLo- Per Heather, this one can be closed in Change Log as ithe 16.3 is very close to being released.
2016-10-25 | 127 |  | Bank Holiday Support (multiple calendars)-OPS - Change Program from Ops Apps to Ops Data (perhaps split and also create piece for IM) | A | AM | Scott | Ann | Ops Apps | Closed | 82 |  |  | 10/25 - sa: PRD created 10/21, work identified for Ops Data and Inv Mgmt, none for Ops Apps. 12/6 - hm: Added to SDLC
2016-10-25 | 128 |  | Add configurations to configuration role - Scope increase | A | GP | Scott | Heather | Ops Apps | Closed |  |  |  | 10/25 - sa: Propose increase in scope from 4 to 8. Increase is as follows: - Base 4 points for the fastest implementation, using primarily hard-coded config lists in front-end and back-end and extending old page layout. - +1 pt for consistency: rewrite config pages from using tabs to matching current left-nav organization. - +1 pt to use dynamic UI list of configuration parameters and validations provided by back-end, instead of hard-coded throwaway work. - +2 pts for dynamic back-end generation of configuration parameters and validations driven by easily extensible configuration metadata, instead of hard-coded throwaway work.
2016-10-26 | 129 |  | Conduct regression Tests -Hardware Refresh | B | GP | Rich | Heather |  | Closed | 15 |  |  | 10/26 QA resources needed for Staging regression testing (DEC) and ATL regression testing. 1/18 CLo- to get estimates from Heather after the new plan is published. 1/25 CLo- Heather/Josh agreed no QA resource is needed for this work for now. Will open a new line when necessary.
2016-10-27 | 130 |  | Unquirk Add Unquirk to the schedule | B | MV | Heather | Heather |  | Closed |  |  |  | 10/27 - hm: Move to January release to ensure December release is stable. 11/1 - hm: Moved to January Release 11/9 - MW: No further action on this. It is in Master and in capacity plan. Closing.
2016-10-28 | 131 |  | OFR-281, change the name of the project to "Fixed Income - Automated Security Setup" | B | GP | Shenba | Heather | Ops Data | Closed |  |  |  | 10/28 - Changing the name of the project in the SDLC to keep it consistent across all documents
2016-10-31 | 132 |  | Advisor-managed preferences project will be split into 2 phases. Please update the existing project name to say "Advisor-managed preferences Phase 1" and add another line for "Advisor-managed preferences Phase 2". The team will work on Phase 1 of the project and the PRD will be complete by 11/15. Phase 2 of the project will be delivered along with the Advisor UI work. I will share the PME for both the phases after discussion with the development team. |  | AM | Shenba | Heather | Advisor | Closed |  |  |  | 1/18 CLo- to check with Shenba. 1/19 CLo- Phase I is planned for AM-2017-02. Closing this line item.
2016-10-31 | 133 |  | Portfolio Management Program Enhancements-ADV | A |  | Heather | Heather |  | Closed | -68 |  |  | 10/31 - hm: Update Portfolio Management Program Enhancements-ADV to reflect 77 days for RMD and earlier start date. Add in 5 days for IM oversight. 11/1 - hm: Master and Capacity Plan updated
2016-11-01 | 134 |  | Assign "Risk-informed Performance" project to Advisor | B | AM | Natalia |  | Adivsor | Closed |  | ADVUI-2017-04 |  | 11/1 - I've confirmed with Justin and Brian that this item (SDLC line 43) does not involve work for Operations and should be assigned to Advisor 12/6 - hm: Risk Informed Performance is in ADVUI.
2016-11-01 | 135 |  | Assign "Export Daily Returns from On-Demand Reporting" project to Ops Data | B | AM | Natalia |  | Ops Data | Closed |  | ADVUI-2017-04 |  | 11/1 - I don't believe that this line item (SDLC line 46) involves work for Ops Apps. If the project is an export of performance numbers then I believe it should be assigned to Ops Data and Ann as PM Owner.
2016-11-02 | 136 |  | EO for Upload orders & allocations to SPS, route to custodians |  | AM | John | Mike | Inv Mgmt | Closed |  | TBD |  | 11/2 - jm: EO is 10 points/60 days 1/18 CLo to check with AM team 1/19 CLo- closed. AM hasn't yet approved.
2016-11-02 | 137 |  | EO for Generate "custodian like" files for delivery to APL managers |  | AM | John | Mike | Ops Data | Closed |  | TBD |  | 11/2 - jm: EO is being reviewed by Ops Data 11/3 - jm: EO is 10 points/60 days 1/18 CLo to check with the AM team. 1/19 CLo- closed. AM hasn't yet approved.
2016-11-02 | 138 |  | Reorganize Advisor UI items based on new EOs and reorg of work into different projects | A | MyVest | Brian | Heather | Advisor | Closed |  | ADVUI-2017-04 |  | 11/2 bkm: Added this item to remind Heather to reorganize the line items in Master based on the new definitions from the Advisor Program. 11/15 CLo- link to Advisors team's Avisor UI Project Estimates: https://docs.google.com/spreadsheets/d/1h-rny2MIdkVvLIB1wRQbamFhh2t91VRl8IxB9W4C1-E/edit#gid=341285534 12/6 - hm: Updated SDLC and Capacity Plans to reflect updated line items and new EOs.
2016-11-02 | 139 |  | Assign "Operations Report Enhancements" to Advisor | B | PCAP | Frederic | Natalia | Advisor | Closed |  | PCAP 16.1 |  | 11/2 - Frederic - a brief justification would be helpful as to why it was agreed upon that Advisor is better suited to do this project. Could you send it to me. 11/1 - Upon review by Kevin Reed, Heather agreed this data belongs to Advisor.
2016-11-03 | 140 |  | Money-Weighted Returns | B | AM | Rob | Ann | Ops Data | Closed | TBD |  |  | 11/10 - MW: AM has requested functional design / sizing of the new - OUT OF SCOPE feature. Product managment to coordinate with AM - provide estimate - then we will review with AM during weekly call to get their acceptance / rejection of the cost and timeline impact. 1/20 CLo this is now tracked via AFR-55. Closing.
2016-11-04 | 141 |  | OFR-318 CR08 - Pin Expansion from 7 digits to 12 digits | B | GP | Shenba | Chris | Advisor | Closed |  |  |  | 11/9 CLo- Added to Master as C-Consider. Waiting for GP to approve the PME (12 days)
2016-11-04 | 142 |  | OFR-319 CP Investment Profile Reporting Accounts | B | GP | Shenba | Chris | Advisor | Closed |  |  |  | 11/9 CLo- Added to Master as C-Consider. Waiting for GP to approve the PME (6 days) | EO
2016-11-04 | 143 |  | OFR-320 CP Create New Household Workflow change | B | GP | Shenba | Chris | Advisor | Closed |  |  |  | 11/9 CLo- Added to Master as C-Consider. Waiting for GP to approve the PME (36 days)
2016-11-04 | 144 |  | OFR-321 CP Error Messaging and UI changes | B | GP | Shenba | Chris | Advisor | Closed |  |  |  | 11/9 CLo- Added to Master as C-Consider.Waiting for GP to approve the PME (3 days)
2016-11-04 | 145 |  | OFR-322 CP Investment Goal change | B | GP | Shenba | Chris | Advisor | Closed |  |  |  | 11/9 CLo- Added to Master as C-Consider. Waiting for GP to approve the PME (6 days)
2016-11-04 | 146 |  | OFR-323 GP Proposal name and portfolio name fields change | B | GP | Shenba | Chris | Advisor | Closed |  |  |  | 11/9 CLo- Added to Master as C-Consider. Waiting for GP to approve the PME (6 days)
2016-11-07 | 147 |  | AssetMark October Release | A | AM | Mark | Heather |  | Closed |  | AM-2016-10 |  | 11/7 - MW: Changing status for these projects to Delivered.
2016-11-07 | 148 |  | EO for trade autoposting logic - PME is 18 days |  | AM | Natalia | Mike | Ops Apps | Closed |  |  |  | 11/7 - EO is 18 days 11/14 - Item is not yet added to Master 11/14 - MW: This is an additional scop item requested by AM. Requires discussion with them RE cost and schedulle impact. 1/18 CLo to check with AM team. 1/19 CLo- closed. AM hasn't yet approved.
2016-11-07 | 149 |  | OFR-270/OFR-272 - MAFS phases 3/4 combined. PME is 272 days | B | GP | Natalia | Chris | Ops Apps | Closed |  |  |  | 11/7 - Ops Apps met with Arlene, Cheryl, and Brian to determine new estimate for MAFS phase 3 and 4 work. Will post the PME to OFR-272 on 11/8 11/10: PME was posted to OFR-272 11/14: Call with GP to discuss estimate. Estimate is not yet approved by client. 12/6 - hm: Approved by Client for Q2 2017 deliverable. | EO
2016-11-09 | 150 |  | AM will probably request this to be back in scope: RP13 (150 Days) - Shadow Account Performance Enhancements |  | AM | Justin | Justin | Ops Data | Closed | 150 Days |  |  | 1/18 CLo to check with AM team. 1/19 CLo- closing this until AM officially requests this via AFR.
2016-11-10 | 151 |  | Drift Review Process | B | AM | Rob | Brian | ? | Duplicate | TBD |  |  | 11/10 - MW: Client has relayed that they sent over a request for design / sizing for this back in July. Rob to follow up on what happened with that request. Product management to coordinate with AM - provide estimate - then we will review with AM during weekly call to get their acceptance / rejection of the cost and timeline impact. 1/18 CLo to check with the AM team. 12/6 - hm: IRR EO delivered to AM, waiting for approval. 1/19 CLo - this is tracked via AFR-75. Closing this line in Change Control.
2016-11-15 | 152 |  | Create additional line item in SDLC for Composite Reporting and assign to Ops Data | A | AM | Natalia | Heather | Ops Data | Closed |  | AM-2017-01 |  | 11/15 - Work for Composite Reporting is split between Ops Data and Ops Apps. Ops Data needs it's own line item to reflect the workload appropriately
2016-11-16 | 153 | AFR-164 | AFR-164 Web service to link SMA account to SMA model | A | AM | John | Heather | IM | AM Cancelled | 12 |  |  | 11/16 - JM: EO is 2 points Required for conversion 1/19 CLo, per Brian, We need to prioritize this one as it is needed for conversion activities. 1/27 CLo- JohnM has logged AFR-164 to track this. EO is ready for review. Next Step: Waiting for AM to approve the EO/PME so that Eng can get this priorized into an AM release ASAP. 2/9 RG: This is original scope and does not require either an EO nor EO approval. Please procede.
2016-11-16 | 154 |  | Bulk change of model targets | A | GP | John | John | IM | Duplicate
2016-11-16 | 155 |  | Add Liquidate to PE | A | GP | John | John | IM | Duplicate
2016-11-16 | 156 |  | Read model web service | A | AM | John | John | IM | Closed |  |  |  | 1/19 CLo- checked with JohnM. This one is now covered by AFR-146 and therefore can be closed.
2016-11-16 | 157 |  | New rebalance frequency - on w/d or model change | A | AM | John | John | IM | Closed |  |  |  | 1/19 CLo- checked with JohnM. Closing this one for now as obsolete. | PRD
2016-11-16 | 158 |  | DMA-like auto-funding | A | AM | John | John | IM | Closed |  |  |  | 1/19 CLo- Checked with JohnM and Brian. Not sure what this was so closing...
2016-11-16 | 159 |  | EO for handling custodian and account number changes - PME is 48 days |  | AM | Natalia | Mike |  | Closed |  |  |  | 11/16: Feature list written and sent to Ops Apps. ETA for having scored by Ops Apps is 11/22. 11/17: Work scored by Ops Apps at 8pts./48 days. Sent out for internal approval 1/19 CLo- closed. AM hasn't yet approved.
2016-11-16 | 160 |  | Request to remove OFR-294 from 16.2.1 and to add OFR-307 | A | GP | Chris | Heather | IM | Closed |  | 16.2.1 |  | 11/16 - Genpact reviewed proposed 2017 release plan with TIAA. TIAA would like us to remove OFR-294 (Leverage Configuration Role for Configurable Parameters) . If possible, they would like to add OFR-307 (DMA Rebalance Extract) This is a net -12 days, but removes from Ops Data and adds to IM 12/6 - hm: Completed
2016-11-16 | 161 |  | Add Liquidate to PE | A | GP | John | John | IM | Closed |  |  |  | 1/19 CLo- checked with JohnM. Closing this one for now as obsolete.
2016-11-16 | 162 |  | Bulk change of model targets | A | GP | John | John | IM | Closed |  |  |  | 1/19 CLo- checked with JohnM. Closing this one for now as obsolete.
2016-11-17 | 163 |  | Non-Custodian Interfaces | B | AM | Brian | Heather | Ops Data | Closed |  |  |  | 11/17 bkm: moved target PRD date to 11/23.
2016-11-17 | 164 |  | Advisor-managed Preferences | B | AM | Brian | Heather | Advisor | Closed |  |  |  | 11/17 bkm: moved target PRD date to 12/15 due to pending requirements from AM.
2016-11-17 | 165 |  | Composite Reporting | B | AM | Brian | Heather | Ops Data | Closed |  |  |  | 11/17 bkm: moved target PRD date to 12/15 due to late start on getting requirements from AM and due to the SME being on vacation for two weeks.
2016-11-17 | 166 |  | AssetMark Personalized QPR commentary | B | AM | Brian | Heather | Advisor | Closed |  |  |  | 11/17 bkm: This will to be moved from Ops Data to Advisor as it primarily involves a UI upload of a document by an Advisor. 12/6 - hm: Updated in Capacity and SDLC
2016-11-18 | 167 |  | Updates to custodian integration dates | B | AM | Frederic | Rob/David | OPS DATA | Closed |  |  |  | 11/18 - Joel is proposing the following new dates for providing the custodian integration ETLs to Ops Data & Overnight for QA: Schwab: 12/2/2016, TD Ameritrade: 12/16/2016, Fidelity: 1/6/2016 Accordingly, Ops Data is planning on allocating QA resources on those dates for the QA cycle with QA to be completed within ten workdays.
2016-11-18 | 168 |  | Updates to custodian integration dates | B | AM | Frederic | Rob/David | OPS DATA | Closed |  |  |  | 11/18 - Joel is proposing the following new dates for providing the custodian integration ETLs to Ops Data & Overnight for QA: Schwab: 12/2/2016, TD Ameritrade: 12/16/2016, Fidelity: 1/6/2016 Accordingly, Ops Data is planning on allocating QA resources on those dates for the QA cycle with QA to be completed within ten workdays. 12/6 - hm: New deliverable dates set.
2016-11-21 | 169 |  | Epic link for Household Overview page |  | AM | Shenba | Brian | Advisor | Closed |  |  |  | Please add AMMO-48184 as the epic for the Advisor UI Household overview page
42695 | 170 |  | Epic link for Household Overview page |  | AM | Shenba | Brian | Advisor | Closed |  |  |  | Please add AMMO-48184 as the epic for the Advisor UI Household overview page 12/6 - hm: Ammo number added
2016-11-21 | 171 |  | OFR-262 (CP Performance Data Report) move from 16.2 to 16.2.2 | A | GP | Frederic | Chris | OPS DATA | Closed |  |  |  | 11/21 - Stored Performance data validation requirements has changed the CP Performance production release date to early January (16.2.2). Chris has confirmed that OFR-262 (CP Performance Data Reports) should also be moved to the 16.2.2 release. OFR-262 is only for GP's internal use and will not be used until CP is enabled.
2016-11-21 | 172 |  | OFR-262 (CP Performance Data Report) move from 16.2 to 16.2.2 | A | GP | Frederic | Chris | OPS DATA | Closed |  |  |  | 11/21 - Stored Performance data validation requirements has changed the CP Performance production release date to early January (16.2.2). Chris has confirmed that OFR-262 (CP Performance Data Reports) should also be moved to the 16.2.2 release. OFR-262 is only for GP's internal use and will not be used until CP is enabled.
2016-11-21 | 173 |  | Please add AMMO-48253 as the Epic # for Advisor Managed Preferences Phase 1 and AMMO-48278 as the epic for OFR-319 |  |  | Shenba | Heather | Advisor | Closed
2016-11-22 | 174 |  | (Not in Master) Web services required for CDA | A | AM | Brian | Heather |  | Closed |  |  |  | 11/22 bkm: Adding this line item back to SDLC as we now know more of the web services required for CDA. 1/18 CLo check with Brian/Rob. 1/19 CLo- closing this line item until we get the list of web services from AM.
2016-11-29 | 175 |  | #REF! | B | AM | Heather | Heather | IM | Closed |  |  |  | 11/29 - hm: Closed out Trade netting. This was delivered in a previous release but kept open waiting for customer response to 1 outstanding question. When the customer responds we will add a new line item in the change control log
2016-11-29 | 176 |  | Please add the Epic Links to the following OFRs. OFR 319 - AMMO-48278 OFR 320 - AMMO-48316 OFR 321 - AMMO-48317 OFR 322 - AMMO-48318 OFR 323 - AMMO-48319 OFR 300 - AMMO-48532 |  | GP | Heather | Shenba | Advisor | Closed
2016-11-30 | 177 |  | Fall Line Securities Implementation | B | FL | Heather | Heather |  | Closed |  |  |  | 11/30 - hm: Confirmed with BM this is unnecessary.
2016-12-02 | 178 |  | Create separate line items for componets of AFR-23 - CDA Integration Withdrawal Reqeusts | A | AM | John | Heather | IM | Closed |  |  |  | To represent the work associated with this feature, create separate line items (and potentially seprate AFRs) for 1) GET SI w.s., 2) GET min/max personalization w.s., 3) GET account w.s., 4) GET portflio w.s, 4) POST raiseandhold w.s., 5) Provde Status Update to AM w.s., 6) Support add'l AM SI frequencies | EO
2016-12-05 | 179 |  | View a terminated account 180 days after closure 12/5/2016 - sa: Propose changing project program owner to Advisor as they confirmed they need to do bulk of the work. Here are the rough initial point estimates provided by program teams. Advisor: Change Advisor UI to view terminated account info, add field, and toggle viewing (TBD pts). Ops Apps: Change Eagle messaging to fail posting if account terminated (2 pts); Ops Data: Restrict loading and/or mark positions and transactions according to availability timeline (1 pt). 1/18 CLo Heather to close this out today. (descoped) | A | AM | Scott |  | Ops Apps | Closed |  |  |  | 12/5/2016 - sa: Propose changing project program owner to Advisor as they confirmed they need to do bulk of the work. Here are the rough initial point estimates provided by program teams. Advisor: Change Advisor UI to view terminated account info, add field, and toggle viewing (TBD pts). Ops Apps: Change Eagle messaging to fail posting if account terminated (2 pts); Ops Data: Restrict loading and/or mark positions and transactions according to availability timeline (1 pt). 1/18/2017 - hm: {roject decsoped, confirmed with Shenba | EO
2016-12-06 | 180 |  | Resolve STAR issue around coupons - Add to 16.2 release | A | GP | Scott |  | Ops Apps | Closed |  |  |  | 12/6/2016 - sa: Cheryl wanted this production bug fix project released in 16.2. Code has been merged and signed off based on Ops testing in Staging 4. 1/20 CLo- closing as this has been delivered to GP via 16.2.
2016-12-06 | 181 |  | Resolve STAR issue around coupons - Add to PCAP 16.3 release | A | PCAP | Scott |  | Ops Apps | Closed |  |  |  | 12/6/2016 - sa: Cheryl wanted this production bug fix project released in PCAP 16.3. Code has been merged and signed off based on Ops testing in PCC Staging. 1/18 CLo- This project is marked as "delivered" via AM-2016-11 on Master
2016-12-14 | 182 | AMMO-48341 | AMMO-48341 - Test coverage for web services | B | MV | Prakash | Prakash | PEng | Closed |  |  |  | Estimate Feb 2017 completion. Ben Dinh will do the majority of the work with ocassional help from Matt Hunter, Wayne Koepcke and Prakash. 1/26 CLo- this has no impact on Capacity Plan. Closing it in Change Log.
2016-12-14 | 183 |  | Webpack testing and deployment | B | MV | Prakash | Prakash | PEng | Closed |  |  |  | Estimated completion: Feb/Mar 2016. Identify how webpack will differ in dev vs test vs staging/production. Plan tests for each environment. 1/18 CLo- to check with Prakash on status. 1/19 CLo- closing as this will not have any impact on Capacity Plan.
2016-12-14 | 184 |  | AMMO-41395 Provide Personalization Reasons feature |  | PCAP | Scott | Heather | IM | Closed | 12 | PCAP 16.3 |  | 12/14 - sa: Ops Apps agreed to take over ownership of this project. Tech lead (Andrew) and Architect (Kevin) to review PRD and confirm that this can be completed for the 16.3 PCAP release. 12/15 - hm: Moved project ownership to Ops Apps
2016-12-19 | 185 | OFR-324 | Request to move OFR-324 (DOL) into 16.2.2 from 17.0) | A | GP | Chris | Heather | Ops Apps | Closed | 70 | 16.2.2 |  | 1/19 CLo- this is in the latest GP plan that Chris shared with Heather this am. Heather to update capacity to reflect the latest GP plan. 1/23 CLo- Chris updated the list in GP Releases. CLo double-checked to make sure everything matches in Master. Closing.
2016-12-19 | 186 | OFR-259 | Request to move OFR-259 into 17.0 (from 17.1) | A | GP | Chris | Heather |  | Closed | 12 | 17 |  | 1/19 CLo- this is in the latest GP plan that Chris shared with Heather this am. Heather to update capacity to reflect the latest GP plan. 1/23 CLo- Chris updated the list in GP Releases. CLo double-checked to make sure everything matches in Master. Closing.
2016-12-19 | 187 |  | Request to add OFR-326 into 16.2.2 | A | GP | Chris | Heather |  | Closed | 48 | 16.2.2 |  | 12/20 - hm: Added to Master and Capacity 2016
2016-12-19 | 188 |  | Request to add OFR-327 into 16.2.2 | A | GP | Chris | Heather |  | Closed | 18 | 16.2.2 |  | 12/20 - hm: Added to Master and Capacity 2016
2016-12-19 | 189 |  | Request to add AMMO-46202 | A | PCAP | Rasaan | Josh |  | Closed | 6 | none |  | 12/20 rm: On-going to project to miograte portfolios with new asset allocations in PCAP production. remaining work is to migrate benchmarks. 1/18 CLo - per the comment on the JIRA ticket, this work is done.
2016-12-20 | 190 |  | (Not in Master) Store transaction descriptions for all pass-through transactions https://jiraw.myvest.com:8443/browse/AMMO-44351 |  | AM | Ann | Joanne | Ops Data | Closed |  |  |  | 1/27- CLo- Joanne reviewed teh AMMO. This is a 2-point feature that can be included AFR-35. We linked this AMMO to the epic and included this AMMO to the RMD for AFR-35.
2016-12-20 | 191 |  | (Not in Master) Convert and store historical market values and performance Required for AM migration and is a prerequisite to Non-Custodian Interfaces | B | AM | Ann | Rob/David | Ops Data | Closed |  |  |  | 1/19 Per Ann, closing this one. not applicable anymore.
2016-12-20 | 192 |  | (Not in Master) Convert and store historical custodial lots and positions Required for AM migration and is a prerequisite to Non-Custodian Interfaces | B | AM | Ann | Rob/David | Ops Data | Closed |  |  |  | 1/19 CLo- per Ann, this one is not needed.
2016-12-20 | 193 |  | (Not in Master) Convert and store historical realized gain/loss Required for AM migration and is a prerequisite to Non-Custodian Interfaces | B | AM | Ann | Rob/David | Ops Data | Closed |  |  |  | 1/19 CLo- this is now tracked via AFR-150.
2016-12-20 | 194 |  | (Not in Master) Implement AssetMark's asset classification scheme. Prerequisite to Non-Custodian Interfaces | B | AM | Ann | Rob/David | Ops Data | Closed |  |  |  | 1/19 CLo- this is now tracked via AFR-151.
2016-12-20 | 195 |  | (Not in Master) Convert and store historical performance and market value. Prerequisite to Non-Custodians Interfaces and Sleeve Performance | B | AM | Ann | Rob/David | Ops Data | Closed |  |  |  | 1/19 CLo- this will be tracked via AFR-110.
2016-12-20 | 196 |  | (Not in Master) Store net investment Prerequisite to Non-Custodian Interfaces | B | AM | Ann | Rob/David | Ops Data | Closed |  |  |  | 1/19 CLo- this is obsolete.
2016-12-20 | 197 |  | (Not in Master) Provide "foundational data" to AssetMark Prerequisite to Non-Custodian Interfaces | B | AM | Ann | Rob/David | Advisor? | Closed |  |  |  | 12/20/16 - ap: AssetMark said that there is a project to provide them with so-called foundational data, which includes things like custodial account number, account identifier, account status, security information, etc. I don't see it anywhere on the SDLC or in JIRA 1/19 CLo- checked with Ann. Closing this one until we get more details from AM.
2016-12-20 | 198 |  | OFR-296 - Add Shenba as ownser, change Pgm Team to Advisor | A | GP | John | Heather | Advisor | Closed | 0 | none |  | 12/20 - jm: change to resources assigned, no change to scope or schedule
2017-01-01 | 199 | AMMO-49275 | AMMO-49275 "Code coverage improvements" | A | MV | Prakash | Prakash | PEng | Closed | 40 |  |  | 1/25 CLo- Prakash's work estimate is 40 days. The work needs to be approved by SDLC and added to the Capacity Plan. 2/2 hm - Added to Capacity, Need to add to Master 2/2 CLo- added to SDLC Master and Harvest
2017-01-18 | 200 | AMMO-49282 | AMMO-49282 Add UI for nightly cycle progress | A | MV | CLo | Prakash | PEng | Needs estimate |  |  |  | 1/18 CLo- Prakash raised that we need to prioritize this one in to the schedule. To be discussed in SDLC.
2017-01-18 | 201 | PCAP-4257 | Provide Personalization Reasons Feature | A | PCAP | CLo | Heather | Ops Apps | Closed |  |  |  | 1/19 CLo- Heather and Rasaan had discussed this. This needs to be moved from 16.3 to 16.3.1 1/31 CLo- this project has been moved to 16.3.1 in Master, but is not on 2017 Capacity Plan. Heather to add it to Capacity for 16.3.1. 2/2 SA - IEE needs to be updated from 12 to 83 (16 already spent, 67 estimated remaining). Also, program was changed from IM to Ops Apps, but program owner is still IM in Master - it should be changed to Ops Apps. 2/2 CLo- updated Program Owner to Ops Apps. Added IEE = 83 to Master. Heather to update Capacity Plan. 2/9 hm - Addede to capacity plan. Still needs link for RMD
|  |  | AMMO-50928 Refactor Selenium Tests | A | MV | Prakash | Prakash | PEng | Needs estimate |  |  |  | 3/01 - Ben is the only person working on this. Expect 30 days to get all Selenium tests to work off of a docker db.
2017-01-20 | 202 | Need JIRA | JWT token authentication | A | All | Heather | Heather | PE | Needs estimate | none if in a release with full regression | GP 17.0 |  | 1/20 hm - JWT and subsequent UI changes for improved, standard left nav common to all roles. This needs to be scheduled for a release that has full regression. Suggest to put this into 17.0. PCAP would pick it up on Q3 17.X release. Need to schedule for AM go live. 1/26 CLo- Prakash's estimate is 30 days. 2/2 Meeting cheduled for 2/10 to discuss timing of this release.
2017-01-20 | 203 |  | Advanced Search, File Cabinet | B | AM | Schenba | Heather | ADV | Closed | 0 |  |  | 1/20 hm: Changes Advanced Search, File Cabinet name to File Cabinet
2017-01-24 | 204 |  | Change to Project Name: Old: non-custodian interfaces New: Interface to send eWM Extract | B | AM | CLo | Heather |  | Closed | none |  |  | 1/24 CLo- the AM project team has decided to rename AFR-35. Capacity Plan needs to be updated with the new name.
2017-01-24 | 205 | AFR-42 | Move "Update UI displays to support option holdings” item from AM-2017-02 to an Advisor UI release | A | AM | Shenba | Heather | Advisor | Closed | -30 |  |  | 1/24/17 Shenba- All the work related to displaying options on Advisor UI will be handled as part of the work for each of the new Advisor UI pages. 1/26/17 CLo- AFR-42 needs to be moved from AM-2017-02 to a later AM release due to its dependency on the ""AdvUI - Holdings"" project, which is currently scheduled for ADVUI-2017-07. 2/2/ CLo- spoke with Shenba. This whole project should be moved to the ADVUI-2017-08. CLo has moved this project from AM-2017-02 to ADVUI-2017-08 in SDLC Master. Heather to update Capacity Plan. 2/9 hm: Cpacit plan updated.
2017-01-25 | 206 | AFR-120 | AFR-120: EOD Allocation File to US Bank | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: TBD; likely 0 as this may not be necessary as a separate file 2/2 hm - This is not a 0 estimate need estimate for configuration and QA. 2/2 CLo- spoke with Joel. Joel is looking to de-scope this project as this is not part of the original scope. Next steps: 1) Rob/David to work with Joel and AM to confirm whether this is needed for Operational Readiness. 2) If this is confirmed as a New Scope item, Rob/David to remove the "z-original scope" label on AFR-120 2/9 RG: confirming with Joel and Justin. 2/9 RG: confirmed with Joel, Justin: AFR-120 is part of original scope. 2/16 JD: Confirmed as required. 2/16 JD: Estimate: 6 days (standard direct to custodian allocation flat file) | Trading partner connectivity
2017-01-25 | 207 | AFR-125 | AFR-125: MF Connectivity to US Bank | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 6 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" Sumary of what needs to be done in SDLC and Capacity: https://docs.google.com/spreadsheets/d/1O524T5nDyGoWCMSVNccDV42VSJUESxhC-UMO83kRlt0/edit | Trading partner connectivity
2017-01-25 | 208 | AFR-126 | AFR-126: MF MV - Sungard connectivity | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 10 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" Sumary of what needs to be done in SDLC and Capacity: https://docs.google.com/spreadsheets/d/1O524T5nDyGoWCMSVNccDV42VSJUESxhC-UMO83kRlt0/edit | Trading partner connectivity
2017-01-25 | 209 | AFR-127 | AFR-127: Equity/ETF SGN Trading Route AMTC | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 4 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" Sumary of what needs to be done in SDLC and Capacity: https://docs.google.com/spreadsheets/d/1O524T5nDyGoWCMSVNccDV42VSJUESxhC-UMO83kRlt0/edit | Trading partner connectivity
2017-01-25 | 210 | AFR-128 | AFR-128: Equity/ETF SGN Trading Route PRS + Allocations | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 4 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" Sumary of what needs to be done in SDLC and Capacity: https://docs.google.com/spreadsheets/d/1O524T5nDyGoWCMSVNccDV42VSJUESxhC-UMO83kRlt0/edit | Trading partner connectivity
2017-01-25 | 211 | AFR-129 | AFR-129: Equity/ETF SGN Trading Route TD + Allocations | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 4 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" Sumary of what needs to be done in SDLC and Capacity: https://docs.google.com/spreadsheets/d/1O524T5nDyGoWCMSVNccDV42VSJUESxhC-UMO83kRlt0/edit | Trading partner connectivity
2017-01-25 | 212 | AFR-130 | AFR-130: Equity/ETF SGN Trading Route Fidelity + Allocations | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 4 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" Sumary of what needs to be done in SDLC and Capacity: https://docs.google.com/spreadsheets/d/1O524T5nDyGoWCMSVNccDV42VSJUESxhC-UMO83kRlt0/edit | Trading partner connectivity
2017-01-25 | 213 | AFR-131 | AFR-131: Equity/ETF SGN Trading Route Schwab | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 4 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" Sumary of what needs to be done in SDLC and Capacity: https://docs.google.com/spreadsheets/d/1O524T5nDyGoWCMSVNccDV42VSJUESxhC-UMO83kRlt0/edit | Trading partner connectivity
2017-01-25 | 214 | AFR-132 | AFR-132: Equity/ETF SGN Trading Route USB | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: TBD; likely 0 as this may not be necessary as a separate connection 2/2 CLo- spoke with Joel. Joel is looking to de-scope this project as this is not part of the original scope. Next steps: 1) Rob/David to work with Joel and AM to confirm whether this is needed for Operational Readiness. 2) If this is confirmed as a New Scope item, Rob/David to remove the "z-original scope" label on AFR-132 2/9 RG: confirming with Joel and Justin. 2/9 RG: confirmed with Joel, Justin: AFR-132 is part of original scope. 2/16 JD: Confirmed a required. 2/16 JD: Estimate: 4 days (standard trading route configuration with SGN) | Trading partner connectivity
2017-01-25 | 215 | AFR-134 | AFR-134: MV - SGN Allocation connectivity | A | AM | Rob | CLo |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 15 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" | Trading partner connectivity
2017-01-25 | 216 | AFR-140 | AFR-140: CDA - Standing Instructions Web Service (was part of AFR-23) | A | AM | Rob | CLo | IM | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work, and had previously been part of AFR-23 (which this partially replaces) 2/1/2017 CLo- the PME for AFR-140 is 106 days. The original estimate on the original CDA work (AFR-23) was 150 days. With this new estimate, we now have 150-106=44 days planned for the remaining CDA work. Sumary of what needs to be done in SDLC and Capacity: https://docs.google.com/spreadsheets/d/1O524T5nDyGoWCMSVNccDV42VSJUESxhC-UMO83kRlt0/edit 2/2 CLo- Brian will work with JM to call out the "new scope" item embedded in this AFR and update the PME. Target Comp Date: early week of 2/6 2/8 CLo- Rob let the MV internal stakeholders know AM needs time to digest what was discussed in the CDA workshop before they can come back with next step. On hold- waiting for AM. 3/1/17 CLo- Next step: move this project to a later AM release as this will not make the original schedule (= AM-2017-03 release). | CDA w/ PME
2017-01-25 | 217 | AFR-141 | AFR-141: CDA - Household Web Service (was part of AFR-23) | A | AM | Rob | Rob/David | ADV | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work, and had previously been part of AFR-23 (which this partially replaces) 2/2 CLo- Brian will work with JM to call out the "new scope" item embedded in this AFR and update the PME. Target Comp Date: early week of 2/6 2/8 CLo- Rob let the MV internal stakeholders know AM needs time to digest what was discussed in the CDA workshop before they can come back with next step. On hold- waiting for AM. | AFR-141
2017-01-25 | 218 | AFR-142 | AFR-142: CDA - Portfolio Web Service (was part of AFR-23) | A | AM | Rob | Rob/David | ADV | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work, and had previously been part of AFR-23 (which this partially replaces) 2/2 CLo- Brian will work with JM to call out the "new scope" item embedded in this AFR and update the PME. Target Comp Date: early week of 2/6 2/8 CLo- Rob let the MV internal stakeholders know AM needs time to digest what was discussed in the CDA workshop before they can come back with next step. On hold- waiting for AM. | AFR-142
2017-01-25 | 219 | AFR-143 | AFR-143: Account Web Service (was part of AFR-23) | A | AM | Rob | Rob/David | ADV | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work, and had previously been part of AFR-23 (which this partially replaces) 2/2 CLo- Brian will work with JM to call out the "new scope" item embedded in this AFR and update the PME. Target Comp Date: early week of 2/6 2/8 CLo- Rob let the MV internal stakeholders know AM needs time to digest what was discussed in the CDA workshop before they can come back with next step. On hold- waiting for AM. | AFR-143
2017-01-25 | 220 | AFR-144 | AFR-144: Member Web Service | A | AM | Rob | Rob/David | ADV | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work, and had previously been part of AFR-23 (which this partially replaces) 2/2 CLo- Brian will work with JM to call out the "new scope" item embedded in this AFR and update the PME. Target Comp Date: early week of 2/6 2/8 CLo- Rob let the MV internal stakeholders know AM needs time to digest what was discussed in the CDA workshop before they can come back with next step. On hold- waiting for AM. | AFR-144
2017-01-25 | 221 | AFR-145 | AFR-145: Personalization Web Service | A | AM | Rob | Rob/David | TBD | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work, and had previously been part of AFR-23 (which this partially replaces) 2/2 CLo- Brian will work with JM to call out the "new scope" item embedded in this AFR and update the PME. Target Comp Date: early week of 2/6 2/8 CLo- Rob let the MV internal stakeholders know AM needs time to digest what was discussed in the CDA workshop before they can come back with next step. On hold- waiting for AM. | AFR-145
2017-01-25 | 222 | AFR-146 | AFR-146: Model Web Service | A | AM | Rob | Heather | IM | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work, and had previously been part of AFR-23 (which this partially replaces) 2/2 CLo- Brian will work with JM to call out the "new scope" item embedded in this AFR and update the PME. Target Comp Date: early week of 2/6 2/8 CLo- Rob let the MV internal stakeholders know AM needs time to digest what was discussed in the CDA workshop before they can come back with next step. On hold- waiting for AM. 2/15 jmm: EO is 2points 2/19 CLo: added AFR-146 to C-Consider on Master. PME 12 days. Capacity Plan to be updated. | CDA w/ PME
2017-01-25 | 223 | AFR-148 | AFR-148: Portfolio Hold Web Service | A | AM | Rob | Natalia | OPS APPs | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 2/2 CLo- Brian will work with JM to call out the "new scope" item embedded in this AFR and update the PME. Target Comp Date: early week of 2/6 2/10/17: We have decided not to write the PRD for the portfolio hold w.s. until we determine if AM has an actual need for advisor level holds to be placed during w.s. | AFR-148
2017-01-25 | 224 | AFR-149 | AFR-149: Account Hold Web Service | A | AM | Rob | Natalia | OPS APPS | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work, and had previously been part of AFR-23 (which this partially replaces) 2/2 CLo- Brian will work with JM to call out the "new scope" item embedded in this AFR and update the PME. Target Comp Date: early week of 2/6 2/8 CLo- Rob let the MV internal stakeholders know AM needs time to digest what was discussed in the CDA workshop before they can come back with next step. On hold- waiting for AM. | AFR-149
2017-01-25 | 225 | AFR-150 | AFR-150: Conversion Tool - convert and store historical realized gain/loss | A | AM | Rob | Heather | ON | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 2/2 CLo - need PME for Capacity Planning 3/1 CLo- entered in SDLC Master (two rows for AM Conversion Tools AFR-150 and AFR-171. PME = 60 days for each.) Capacity Plan to be updated. | AFR-150
2017-01-25 | 226 | AFR-151 | AFR-151: Conversion Tool - implement AM's asset classification scheme | A | AM | Rob |  | ON | Duplicate |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/26/17 This used to be on the SDLC and is now missing. It is on the AM tabs but missing the reference on Master. Please re-add? (You can find it on back up copies of the SDLC going back to 10/21/16. It had status = C-Consider.) 2/2 CLo- need PME for Capacity Planning. 2/9 CLo- Ann and I found out this is a duplicate of AFR-51. Closing AFR-151. | AFR-151
2017-01-25 | 227 | AFR-34 | AFR-34 Composite Reporting | A | AM | Brian | CLo | Ops Apps | AM Cancelled |  |  |  | 1/25/17 bkm: Modified target PRD date to 2/28 as requirements process is just starting on 1/26 with onsite meeting at AM. Also, I think this should be reassigned to Ops Data, correct? 1/26/17 CLo- it's been reassigned to Ops Data. 2/2 CLo- next step: Rob/David to update AM with the new PRD Target Date. 2/9 RG: Revised PRD date was communicated on PRD Report on 1/27... but I updated on JIRA just now for good measure.
2017-01-25 | 228 | AFR-69 | AFR-69: Equity/Fixed Income EOD file forAMTC client level allocations | A | AM | Rob | Heather |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 6 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" | Trading partner connectivity
2017-01-25 | 229 | AFR-70 | AFR-70: MFEOD order file for Pershing | A | AM | Rob | Heather |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 6 days 2/2/ CLo- Project added to SDLC Master. Heather to add this project to Capacity and remove the two placeholders for "Trading Partner Connectivity" and "Trading Partner Connectivity-MV" | Trading partner connectivity
2017-01-25 | 230 | AFR-71 | AFR-71: MF Connectivity to Fidelity (SGN) | A | AM | Rob | Heather |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 0 days (included in AFR-130 work) 2/2 CLo - Rob/David to confirm AFR-130 is sufficient here and no extra work is needed. 2/10 RG: Confirmed with Joel, AFRs 71 and 130 are both needed. | Trading partner connectivity
2017-01-25 | 231 | AFR-72 | AFR-72: MF Connectivity to TD | A | AM | Rob | Heather |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 0 days (included in AFR-129 work) 2/2CLo - Rob/David to confirm AFR-129 is sufficient here and no extra work is needed. 2/9 RG: Confirmed with Joel, AFRs 72 and 129 are both needed. 2/16 JD: AssetMark is now looking to do this as a flat file, so the work would no longer be included in AFR-129. 2/16 JD: Estimate 6 days (standard flat mutual fund order file) | Trading partner connectivity
2017-01-25 | 232 | AFR-73 | AFR-73: MF Connectivity to Schwab (SGN) | A | AM | Rob | Heather |  | AM Cancelled |  |  |  | 1/26/17: RG- this is part of originally contracted work 1/28 CLo- spoke with Joel. Joel and Leland just finished the estimates today. Joel to update the Change Log with the estimate soon. 1/28 JD Estimate: 0 days (included in AFR-131 work) 2/2 CLo- Rob/David to confirm AFR-131 is sufficient here and no extra work is needed. 2/9 RG: Confirmed with Joel, AFRs 73 and 131 are both needed. | Trading partner connectivity
2017-01-25 | 233 | AMMO-46229 | (Not in Master) Conversion Tool: enable adHoc parse and PassThroughHandler job for loading conversion data AMMO-46229 | A | AM | Heather | Heather | ON | AM Cancelled |  |  |  | 1/26/17 hm: During the AssetMark "operational pilot" we want to evaluate using the existing SPS Transaction ("PassThrough") process to convert position data. To do this, we will load positions as Receive (REC) Transactions and send them to STAR. 1/27 CLo- the AMMO is assigned to Joel right now. MikeB worked on it a few weeks ago (and billed the time to the "AM Environment Development" project in JIRA)
2017-01-25 | 234 | AMMO-49409 | AMMO-49409, AMMO-49502 AssetMark web service enhancements | A | AM | Prakash | Prakash | PEng | Closed | 10 |  |  | 1/27 CLo- Prakash's estimate is 10 days. 1/28 CLo- clo to talk with prakash. can be treated as bug fixes 2/6 CLo- added AMMO-49409 to Harvest as a bug fix for AAT-20
2017-01-26 | 235 | AFR-21 | AFR-21 : Link Multiple Groups of Portfolios in a Household Closed in JIRA as "not needed" but still in SDLC Master. | A | AM | CLo | Heather | Ops Data | AM Cancelled | 70 |  |  | 2/2 CLo- Heather/Rob/David/CLo discuss this today. Next Step: Rob/David to confirm with AM AFR-21 is indeed no longer needed. Once we have confirmation from AM, Heather will remove it from Capacity Plan. 2/9 RG: This is confirmed by AM. Please update capacity plan!
2017-01-26 | 236 | N/A | PCAP 16.3.1 Planning | B | PCAP | CLo | Rasaan |  | Open |  |  |  | 1/26/17 CLo- Rasaan is still working through the final list of AMMO's for consideration. Link to PCAP 16.3.1. Planning Worksheet: https://docs.google.com/spreadsheets/d/1IwgooDOdC_TEPyvGn9yZiRIN-WKY_jxO0fbovH9qmHQ/edit?ts=588a4b4d#gid=0
2017-01-26 | 237 | OFR-320 | OFR-320 CP Create New Household Workflow change | C | GP | Shenba | CLo | Advisor | Capacity to be updated |  |  |  | Due to the change in the requirement request by TIAA, the PME increased by 2 days. TIAA has approved the new PME of 38 days.
2017-01-26 | 238 |  | AFR-44 Multiple Withdrawals to Fulfill a Standing Instruction Based on AM Methodology the AFR itself has been canceled/closed in JIRA, but in Master it's still part of the AM-2017-07 release. | A | AM | CLo | Rob/David |  | duplicate |  |  |  | dupliate of row 216.
2017-01-26 | 239 | AFR-51 | AFR-51: AssetMark Security Classification | A | AM | Rob | Ann |  | duplicate |  |  |  | 1/26/17 This used to be on the SDLC and is now missing. It is on the AM tabs but missing the reference on Master. Please re-add? (You can find it on back up copies of the SDLC going back to 10/21/16. It had status = C-Consider.) | AFR-51
2017-01-26 | 240 |  | AFR-44 | A | AM | John | Rob/David | Inv Mgmt | Duplicate |  |  |  | 1/26/17 jmm: Based on the revised plan for AM to handle this matching logic, the feature is no longer required. the JIRA is already closed. 1/28/17- CLo- thanks for adding this to Change Log. There was already another line item for the same topic. I'll close this one as a duplicate.
2017-01-27 | 241 | AFR-25 | AFR-25: View a terminated account 180 days after closure | A | AM | CLo | Heather | Ops Apps? | AM Cancelled |  |  |  | 1/27 CLo- Shenba to provide the PME for the UI portion (that will be part of the ADVUI). Once we have the PME, we'll re-calc the estimate for the remaining back-end work and fit the project in to Capacity Plan. 2/24 CLo- Shenba provided the EO (PME = 53 days) today.
2017-02-24 | 242 | ADVUI | (derived from AFR-25) View a terminated account 180 days after closure | A | AM | CLo | Heather | Advisor | AM Cancelled
2017-01-27 | 243 | AFR-37 | AFR-37 Funding Account | A | AM | CLo | Rob/David | IM | AM Cancelled |  |  |  | 1/27 CLo- AFR-37 has been moved from AM-2017-02 to AM-2017-04 in the Capacity Plan. PRD needs to be ready-enough for Eng by 2/15/17. Next: Rob/David to work with AM to unblock JohnM. 2/9: Updated AFR to indicate on AFR that the requirements delay is putting the 4/26 UAT target at risk. 2/10 CLo- Rob/David, please raise this with AM.
2017-01-27 | 244 | AFR-4 | AFR-4 The project name has been changed by AM. | B | AM | CLo | Heather | OPS DATA | AM Cancelled |  |  |  | 1/27 CLo- Project Name has been updated in SDLC and Harvest. Heather to update the project name in Capacity Plan 2/24 jmm: change Pgm Team responsibility from Inv Mgmt to Ops Data, JM to retain PM Ownership. 2/24 clo: Program Team has been updated in SDLC Master. Capacity to be updated.
2017-01-27 | 245 | AFR-53 | AFR-53 Advisor-managed Preferences (QPR) | A | AM | CLo | Shenba | Advisor | AM Cancelled |  |  |  | 1/27 CLo- the project name has been changed with "(QPR"). CLo to make sure the name is updated in Harvest and JIRA. 1/27 CLo- next steps: 1) Shenba to confirm which ADVUI project this is contained. 2) Heather/CLo to recalc the estimate for the non-ADVUI portion and compare the new estimate with RMD for QPR..
2017-01-27 | 246 | AFR-44 | AFR-44 Multiple Withdrawals to Fulfill a Standing Instruction Based on AM Methodology | B | AM | CLo | Heather |  | AM Cancelled | -70 |  |  | 1/26/17 CLo- AFR-44 itself has been canceled/closed in JIRA, but in Master it's still part of the AM-2017-07 release. 1/29/17 RG: CONFIRMING CLo's 1/26 comment. This is descoped. Please indicate Z-DESCOPED on Master. 2/2/17 CLo- AFR-44 is now marked as "DESCOPE" in SDLC Master and is archived in Harvest. Heather to update Capacity Plan.
2017-01-30 | 247 | AMMO-50239 | Spring upgrade 4.3.6 | B | MV | Prakash | Heather | PEng | Capacity to be updated |  | Consider |  | This will need full regression.
2017-01-30 | 248 | OFR-323 | GP changed the requirement to not add a number as a suffix to both portfolio and proposal names | A | GP | Shenba | Heather | Advisor | Closed |  |  |  | The estimate for the change is 1 point. This change should be part of 16.2.2 release. 2/2 CLo- in SDLC Master, PME = 6 days and IEE = 13 days
2017-01-31 | 249 | AMMO-49971 | Request to add SDLC line item for: Retire Ops Console Module for PCAP | B | PCAP | Natalia | Heather | Ops Apps | Open |  |  |  | 1/31/17 NG - Rasaan has filed an epic AMMO to handle the needed work to fully retire Ops console for PCAP. I would like to get this added to the SDLC as a project. 2/1/17 SA: We’ve completed our preliminary analysis of Ops Apps’ 3 tickets to Retire Ops Console. Total of 4 points to make changes and fully feature test. The story points on each ticket is accurate and captures the breakdown. Please note that this does NOT include an estimate for the ticket assigned to IM. 3/6/17: Moved this back to Open - I don't believe we're waiting on Product for this. Would like it added to the Master tab so we can allocate resources for it accordingly.
(original date) 8/18/16 | 250 | AFR-51 | Why was AFR-51 (AssetMark Security Classification) dropped from this list? | A | AM | Rob | Brian | Ops Data | AM Cancelled |  |  |  | 1/27/17 RG: This is making my PRD report look bad. Can we come up with a better way to communicate that this is on hold rather than stripping it from the SDLC entirely? 2/1/17 CLo- this project is back on SDLC Master under "Consider" Next steps: 1) Rob/David to let AM know MV PM is waiting for clarifications from them (see comments in AFR-51.) 2) Once AM answers our questions in AFR-51, Brian/Shenba/Ann to provide PME so that we can work AFR-51 in to the Capacity Plan. 2/9 RG: As of 2/3, we received the information back that we needed. Brian saw this and updated the ticket to Josh M. Next steps are on Josh M. 2/10 RG: PME = Brian is still tracking down details with AM. | AFR-51
2016-08-12 | 251 |  | Ops Apps Prioritization for AM5 | A | AM |  | Heather | Ops App | Closed |  | AM 5 |  | 8/12 need to move ~ 50 hours out of AM 5 to after 16.2. Otions include: Break up Slleve performance into phases and prioritize, CDA workflow integration. Ability to view terminated account for 180 days. 8/25 - prioritization no longer an issue.
2016-10-20 | 252 |  | Non-Custodian Interfaces - on SDLC twice | B | AM | Brian | Heather |  | Closed |  | AM-2017-01 |  | 10/20 bkm - We should delete duplicate line item
2016-11-29 | 253 |  | UI for Preference Section Advisor UI Preferences - Duplicate rows | B | AM | Brian | Heather |  | Closed | -50 | ADVUI-2017-04 |  | 10/20 bkm - we should delete UI for Preference Section line item as it is covered in Advisor - managed Preferences 10/24 - hm: UI for Preference Section descoped.
2016-11-29 | 254 |  | Billing changes to Support Tax Shield and Goals | B | AM | Heather | Heather |  | Closed |  |  |  | 11/29 - hm: Clean up items under consideration 1/19 CLo- out of date. Closing 2/2 CLo- removed this project from the Consider section. This line did not have any info except for the project name.
2016-08-11 | 255 |  | Unquirk Add Unquirk to the schedule | B | MV |  | Heather |  | Closed | 280 |  |  | 8/11 Add to SDLC and Capacity Plan - Heather 8/12 Added to Capacity Plan 08/08 Control 10/24 - hm: Added to Master
2017-02-01 | 256 | AFR-5 | Target Dev Complete has changed from 1/31/17 to 2/8/17 (still on track for AM 2017-02 release) | B | AM | CLo | CLo |  | AM Cancelled |  |  |  | 2/1 CLo - Per Sajid, AFR-5 is still on track to be released in the AM-2017-02 release. 2/9 rg: @CLo - is there an action needed here for the AM Field Team?
2017-02-01 | 257 | OFR-259 | SDLC and Capacity need to be updated: 1) Program Team = Ops Data, PM = AP 2) There are two entries in both SDLC Master and in Capacity Plan- one in 17.0 and one in 17.2. Chris has confirmed this should be in 17.0, not 17.2. | B | GP | Chris | Heather | Ops Data | Capacity to be updated |  |  |  | 2/1 CLo- updated the program team in SDLC Master. Removed the duplicate project from 17.2 release. Next step: Heather to update the program team for this project in Capaicty Plan.
2017-02-01 | 258 |  | New Advisor UI project: ADVUI - Advisor Managed Preferences - UI Work | B | MV | CLo | Heather | ADV | Capacity to be updated |  |  |  | 2/2 CLo- per Shenba, this project should be added to ADVUI-2017-08. EO is here: https://docs.google.com/spreadsheets/d/1h1vLbdVm47hUZito839s-0I0jGLqXeSVkHTKgm7gpLI/edit#gid=0 2/2/ CLo- Added to SDLC Master and Harvest. Heather to add this project to Capacity Plan. 3/7 CLo- the project will be prioritized among other projects for AM Plan B. Closing this item in the Change Log.
2017-02-01 | 259 |  | New ADvisor UI project: Personalization and Standing Instructions Page | B | MV | CLo | Heather | ADV | Closed |  |  |  | 2/2 CLo- per Shenba this project should be added to ADVUI-2017-08. EO is here:https://docs.google.com/spreadsheets/d/194S2ManAZvamxXQNyoiz4H_z4T2SxmkReFAQEhIXSW8/edit#gid=0 2/2/ CLo- Added to SDCL Master and Harvest. Heather to add this project to Capacity plan. 3/7 CLo- the project will be prioritized among other projects for AM Plan B. Closing this item in the Change Log.
2017-02-02 | 260 | OFR-326; OFR-327 | Move these two OFRs to 17.0 | A | GP | Chris | Heather | ADV | Closed |  |  |  | 2/2 - The PRDs for both of these items are currently in review still. Given that dev complete for 16.2.2 is 2 weeks out, we would ask that these be pushed into 17.0. Genpact has asked if we can produce sample payloads at the end of February for OFR-326, as they need to provide to TIAA for their development efforts 2/2 CLo- updated the Release in SDLC Master. Heather to update Capacity Plan.
2017-02-02 | 261 | AFR-18 | AFR-18: (already delivered in AM4) Integration between SMI and SPS | B | AM | CLo | CLo | IM | Closed |  |  |  | 2/2 CLo- thi project has been listed as a "candidate project" in SDLC, but according to the JIRA ticket, AFR-18 was delivered via AM4. Updating the project in Master and AM Releases tab.
2017-02-02 | 262 | AMMO-37862 | AMMO-37862 Wake Up for SI's should turn "off" when cash is raised | C | PCAP | CLo | CLo |  | Closed |  |  |  | 2/2 CLo- this one has been in SDLC Master > Consider for a long time. Rasaan agreed that this can be removed from Master until there's a plan to implement the feature in a release.
2017-02-02 | 263 | AMMO-39100 | AMMO-39100 Provide Fee Discount feature | C | PCAP | CLo | CLo | Ops App | Closed |  |  |  | 2/2 CLo- this one has been in SDLC Master > Consider for a long time. Rasaan agreed that this can be removed from Master until there's a plan to implement the feature in a release.
2017-02-02 | 264 | PCAP-4257 | Provide Personalization Reasons feature | A | PCAP | Scott |  | Ops App | Duplicate |  |  |  | 2/2 SA - IEE needs to be updated from 12 to 83 (16 already spent, 67 estimated remaining). Also, program was changed from IM to Ops Apps, but program owner is still IM in Master - it should be changed to Ops Apps. 2/2 CLo- this is a duplicate of Change #201. I've copied/pasted Scott's comment to Change #201. Closing this as a duplicate.
2017-02-06 | 265 | OFR-324 | TAAA PA - DOL Fee Changes | A | GP | CLo | Chris | Ops Apps | Waiting for CS |  |  |  | 2/14 NG - Scope change from client on 1/31/2017. Revised PME of 81-129 days posted to GP on 2/10/2017. PME approved by client 2/14/2017. OFR has fix version of 17.0. Can we please get this item updated on the master tab to reflect the 17.0 release. 2/15 CLo- Updated PME with 129 days in Master. Next Step: Chris to confirm whether this is in or out of scope for 17.0 due to the delay.
2017-02-06 | 266 | AFR-171 | AM Conversion: Load and Store Historical MVs and Performance | A | AM | CLo | Heather | Ops Data | AM Cancelled |  |  |  | 2/8 CLo- this is one of the 3 AFRs that are considered "the original scope" for Conversion Tool. AnnP is actively working on the PRD for AFR-171 so we need to get this on SDLC/Capacity/Harvest soon. 2/28 CLo- we now have only 2 AFRs for Conversion Tools (AFR-150 and AFR-171, PME = 75 days each.) 3/1 CLo- entered in SDLC Master (two rows for AM Conversion Tools AFR-150 and AFR-171. PME = 60 days for each.) Capacity Plan to be updated.
2017-02-08 | 267 | AFR-140 | CDA Workflow - Standing Instructions Web Service | A | AM | John | David | Inv Mgmt | AM Cancelled |  |  |  | 2/8: -jmm - Internal PRD review is required before posting for AM approval. Timing of these two steps puts delivery in AM-2017-03 at risk. The release date corresponds to AFR-23, not AFR-140.
2017-02-08 | 268 | OFR-325 | Add to Master Project Name: Remove the Manage Inactive Link for all OpenWealth Sponsors | A | GP | John | CLo | Inv Mgmt | Capacity to be updated |  |  |  | 2/8 - jmm - PRD approved, RMD in progress, not in SDLC. 2/10 CLo- Checked with Chris. Heather has agreed to 325 in 16.2.2 and we have pushed 331 to 17.0. 2/10 CLo- added this project to SDLC Master and Harvest. Next Step: Heather to update the Capacity Plan.
2/10./17 | 269 | OFR-331 | Add to Master: Project Name: PA Auto Substitution Account Setting Change | A | GP | John | CLo | Inv Mgmt | Capacity to be updated |  |  |  | 2/8 - jmm - PRD approved, RMD in progress, not in SDLC. 2/10 CLo- Checked with Chris. Heather has agreed to 325 in 16.2.2 and we have pushed 331 to 17.0. 2/10 CLo- added this project to SDLC Master and Harvest. Next Step: Heather to update the Capacity Plan.
2017-02-13 | 270 | AFR-48 | PRD Required Start Date and Dev Start Dates are in 2018... typo? | C | AM | Rob | CLo | n/a | AM Cancelled
2017-02-14 | 271 | OFR-326 | New web services for client and account adding/updating | A | GP | Heather | CLo | ADV | Capacity to be updated | -10 |  |  | 2/14 hm: Customer descoped from 17.0 2/14 CLo- moved this project to consider. Next step: Heather to update the Capacity Plan.
2017-02-17 | 272 | AMMO-48394 | New web services for client and account adding/updating | A | AM | CLo |  |  | AM Cancelled
2017-02-17 | 273 | AFR-94 | Original Scope Project Name: Expose all GET/Read onboarding web services data elements passed | A | AM | CLo | ? | TBD | AM Cancelled |  |  |  | 2/13 CLo- Rob let me know AM has marked AFR-94 as the highest priority item. Next steps: 1) AM Field Team to confirm with AM on the priority. 2) CLo to work with internal teams to figure out the PM/PO and program team assignment.
2017-02-15 | 274 | PCAPFR-24 | Add Initial Implementation & Strategy Change to Manual Non Strategy Frequency | A | PCAP | John | CLo | InvMgmt | Internal PRD review req'd | 2 | PCAP 16.3.1 | New Feature | 2/15 jmm: EO is 2 pts, needs to be approved
2017-02-15 | 275 | PCAPFR-25 | Apply Purchase Threshold Request to All Positions | A | PCAP | John | CLo | InvMgmt | Needs estimate |  | PCAP 16.3.1 | New Feature | 2/15 jmm: EO forthcoming, will need approval once delivered
| 276 | PCAP-4257 | Provide Personalization Reasons Feature | B | PCAP | Scott |  | Ops Apps | Open | -10 | PCAP 16.3.1 |  | 2/15 sa: Revised QA estimates: Advisor +3 (4 to 7); Ops Data -5 (15 to 10). Lowers IEE from 83 to 81. Estimates across program teams may be reduced further, with revisions from IM expected by Tuesday 2/21. 3/1 sa: Revised QA estimates: IM -5 (14 to 9). Lowers IEE further to 76. Ops Apps estimate may be reduced further, eta for that update on 3/2. 3/2 sa: Revised QA estimate: Ops Apps. (9 to 6). Lowers IEE further to 73.
2017-02-21 | 277 | ADVUI | ADVUI - Investment Change History | B | AM | CLo | CLo | ADV | AM Cancelled |  |  |  | 2/21 CLo- Shenba let me know this new advisor UI project needs to be added to SDLC Master, Capacity, and Harvest.
2017-02-22 | 278 | AFR-4 | Income SWP Reserve | A | AM | John | David | Inv Mgmt | AM Cancelled |  | AM-2017-03 |  | 2/22 jmm: At risk for delivery in March release
2017-02-23 | 279 | PCAPFR-15 | Exclude from Strategy Personalization - Prorate Inclusive of Future Changes | A | PCAP | John | CLo | Inv Mgmt | Open |  | PCAP 16.3.1 |  | 2/23 jmm: EO 2.5 pts, needs to be approved
2017-02-23 | 280 | AFR-141,AFR-142.,AFR-143, AF$-144 | CDA Workflow - Household/Portfolio/Account/Member Web Services | A | AM | Shenba | CLo | ADV | AM Cancelled |  |  |  | 2/23 These AFRs are required to complete the CDA workflow web services requests and needs to be added to the SDLC document. All of the AFRs can be added as one project since they are all related. I will forward the EO document
2017-02-23 | 281 | OFR-272 | Rename SDLC line item #17 (MAFS Fees Project Phases 3 & 4) to reflect reduced scope. New PRD name is: Portfolio Fee Assignment Audit & Discount UI Update | B | GP | Natalia | CLo | Ops Apps | Open | -175 | 17 | Reduced Scope | 2/23/17: The MAFS phase 3 & 4 project has been dramatically reduced in scope and no longer contains any of the original work slated for MAFS 3/4. As a result, I've renamed the PRD to reflect the work we are doing and would like the SDLC master tab updated to reflect the current PRD.
| 282 | AFR-4 | Income SWP Reserve | A | AM | John | CLo | Ops Data | Closed |  |  |  | 2/24 jmm: change Pgm Team responsibility from Inv Mgmt to Ops Data, JM to retain PM Ownership 2/24 clo: Program Team has been updated in SDLC Master. Also, this Change Log item (ID 282) has been combined with Change Log ID 244. Closing.
2017-03-01 | 283 | ADVUI | Please add the following new projects to the list of ADVUI projects. These projects can be scheduled for the last ADVUI release. The EOs for these projects will be forwarded in an email. 1. MyBook Scatter Plot 2. ADVUI - Page Refresh and Back Button Functionality | B | AM | Shenba | CLo | ADV | AM Cancelled |  |  |  | The MyBook page enhancement was suggested by Anton. The team wanted to add the back button and page refresh functionality as a separate project.
2017-03-01 | 284 | PCAP-4257, AMMO-50689 | Pricing Hierarchy - Updated IEE | A | AM | Scott |  | Ops Apps | Closed |  | AM-2017-03 |  | 3/1 sa: Updated IEE from 54 to 50.
2017-03-01 | 285 | OFR-272, AMMO-43772 | MAFS Fees Project Phases 3 & 4 - May have been renamed to Portfolio Fee Assignment Audit & Discount UI Update (see change control ID 281) - Updated IEE | A | GP | Scott |  | Ops Apps | Open |  | 17.0 |  | 3/1 sa: Updated IEE from blank to 18.
2017-03-01 | 286 | AMMO-49006 | DOL - Changes Regulatory requirements - Updated IEE | A | GP | Scott |  | Ops Apps | Open |  | 17.0 |  | 3/1 sa: Updated IEE from blank to 127.
2017-03-01 | 284 | AFR-153 | CDA
Changes Identified:
|  |  | 2016-05-01 | 0
|  |  | 2016-06-01 | 0
|  |  | 2016-07-01 | 11
|  |  | 2016-08-01 | 28
|  |  | 2016-09-01 | 51
|  |  | 2016-10-01 | 46
|  |  | 2016-11-01 | 44
|  |  | 2016-12-01 | 21